## Workplan
2010-2012 Regional Climate and Energy Action Workplan
| * * *Final Revisions Adopted May 25, 2011, by COG Climate Energy and Environment Policy Committee* * * |  |  |  | 2010 |  |  |  | 2011 |  |  |  | 2012
|  | Recommendations Performance Measures (a) |  | Responsible Parties | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | Emission Impact
Legend
|  | Orange | Proposed Deletion
|  | Blue | Proposed Addition or Revision
ROW ID | I. Regional Greenhouse Gas Reduction Goals/Plans
1 |  | 2012 GOAL: Reduce Greenhouse Gas Emissions to 2005 Levels |  | Region | [12 empty] | Yes | bar: 2012 4th
2
3 |  | Regional Plan to Meet 2012 Goal
4 |  |  | Prepare plan to reduce greenhouse gas emissions in the region to 2005 levels by 2012. | Local Governments, COG, Community (Business and Individuals) | [12 empty] | Yes | bar: 2010 1st
5 |  |  | Identify work program priorities for the calendar year. | CEEPC | bar: 2010 1st; 2011 1st; 2012 1st
6
7 |  | Inventories
8 |  |  | Provide technical support to individual local governments for developing greenhouse gas emission inventories (including fact sheets, calculators, and workshops focused on activity data, emission factors, and protocols/methodologies). | COG, ICLEI, EPA, WRI, The Climate Registry | bar: 2010 2nd; 2011 1st; 2012 1st
9 |  |  | 50% of jurisdictions prepare government and community wide greenhouse gas inventories. | Local Governments | bar: 2010 3rd
10 |  |  | 100% of jurisdictions prepare government and community wide greenhouse gas inventories. | Local Governments | bar: 2011 3rd
11
12 |  | Local Climate and Energy Plans
13 |  |  | 50% of jurisdictions prepare plan to reduce greenhouse gas emissions from government operations, including adopting a reduction target. | Local Governments | [12 empty] | Yes | bar: 2010 4th
14 |  |  | 100% of jurisdictions prepare plan to reduce greenhouse gas emissions from government operations, including adopting a reduction target. | Local Governments | [12 empty] | Yes | bar: 2011 4th
15 |  |  | 50% of jurisdictions prepare community-wide plans to reduce greenhouse gas emissions. | Local Governments | bar: 2011 4th
16 |  |  | 100% of jurisdictions prepare community-wide plans to reduce greenhouse gas emissions. | Local Governments | [12 empty] | Yes | bar: 2012 4th
17 |  |  | Adopt plans to reduce emissions from the aviation sector, including adopting a reduction target. | MWAA | [12 empty] | Yes | bar: 2010 4th
18 |  |  | Evaluate cost effectiveness of key actions to meet the 2012 goal. | COG | bar: 2010 4th
19
20 |  | Tracking and Reporting
21 |  |  | Develop system for tracking progress toward greenhouse gas reduction goals and periodically review targets. | COG, Local Governments, Utilities | bar: 2010 2nd
22 |  |  | Provide progress reports for use by COG in developing annual regional progress report on work plan implementation. | Local Governments | bar: 2010 1st; 2011 1st; 2012 1st
23 |  |  | Prepare annual progress report on meeting the 2012 goal and associated work plan targets. | COG | bar: 2010 2nd; 2011 2nd; 2012 2nd
24
25 |  | Other Activities
26 |  |  | Prepare regional economic development plan to include consideration of green jobs assessment. | COG | bar: 2012 4th
27
28 |  | Mid-Term Reduction Targets
29 |  | 2020 Goal: Reduce Greenhouse Gas Emissions 20% below 2005 Levels
30 |  |  | Adopt plan to meet 2020 Goal. | COG | [12 empty] | Yes | bar: 2012 4th
Note: (a) Recommendations and Performance Measures are intended for those jurisdictions where implementing authority exists.
31 | II. Energy
32
33 |  | A. Energy Efficiency
34
35 |  | Green Building Policy
36 |  |  | 100% of jurisdictions adopt and implement COG Green Building Policy (e.g., all new public sector buildings achieve at least LEED Silver levels and all private-sector commercial buildings. meet a regional LEED-certified plus standard or equivalent. Adopted by COG Board in November, 2007). | Local Governments, IGBG, USGBC | [12 empty] | Yes | bar: 2011 1st
37 |  |  | Propose Green Building Policy Recommendations for schools and residential buildings. | IGBG, Local Governments | bar: 2011 4th
38 |  |  | Evaluate and develop recommendations for enhancements to building codes for energy efficiency. | IGBG, EAC, Local Governments | bar: 2011 3rd
39 |  |  | Evaluate and develop green affordable housing policy and program recommendations. | IGBG, COG Regional Affordable Housing Partnership, Local Governments | bar: 2012 1st
40 |  |  | Promote neighborhood scale green design and smart growth principals. | IGBG, MDPC, Local Governments | bar: 2011 4th
41
42 |  | Municipal Energy Conservation
43 |  |  | 100% of jurisdictions reduce energy use by 10% below business-as-usual by 2012 (return to 2005 levels). | Local Governments | [12 empty] | Yes | bar: 2012 4th
44 |  |  | 60% of jurisdictions implement a program to replace older street lights with new more efficient technology. | Local Governments, COG, Utilities, Vendors | [12 empty] | Yes | bar: 2012 2nd
45 |  |  | 50% of jurisdictions use energy performance contracting in at least one building retrofit project. | Local Governments, ESCOs | [12 empty] | Yes | bar: 2012 2nd
46 |  |  | 3 regional projects implemented for LEED-EB Operations and Maintenance. | Local Governments, Private Sector | [12 empty] | Yes | bar: 2012 3rd
47
48 |  | Building Benchmarking
49 |  |  | 80% of jurisdictions track and benchmark energy performance in all government buildings. | Local Governments | bar: 2012 2nd
50 |  |  | 60% of jurisdictions disclose energy performance in all government buildings. | Local Governments | bar: 2012 2nd
51 |  |  | 50% of jurisdictions have commercial building energy usage benchmarking requirements. | Local Governments | bar: 2012 4th
52
53 |  | Energy Challenge Programs
54 |  |  | 35% of jurisdictions develop energy challenge/pledge programs (community, citizens) and/or encourage energy leaders programs. | Local Governments, Private Sector | [12 empty] | Yes | bar: 2011 1st
55 |  |  | 35% of jurisdictions develop green business challenges or certifications (businesses, employees). | Local Governments, Private Sector, Greater Washington Board of Trade | [12 empty] | Yes | bar: 2011 1st
Note: (a) Recommendations and Performance Measures are intended for those jurisdictions where implementing authority exists.
56 |  | Financing and Supporting Energy Efficiency Investments
57 |  |  | Standardize training and certification of energy auditors and home and building energy retrofit and conservation contractors, facilitating reciprocity across the region. | State Energy Offices, Weatherization Programs, Community Colleges, Building Performance Institute, RESNET | bar: 2010 4th
57a |  |  | Continue to promote training and certification of energy auditors. | State Energy Offices, Weatherization Programs, Community Colleges, Building Performance Institute, RESNET | bar: 2011 4th; 2012 4th
58 |  |  | Prepare a matrix of financing options and recommendations for innovative financing programs for energy efficiency for single and/or multifamily homes. | COG, Local Governments | bar: 2010 3rd
58a |  |  | Track and advocate actions to overcome federal obstacles to municipal financial programs. | COG, Local Governments | bar: 2011 4th; 2012 4th
60 |  |  | Prepare report on barriers to invest in energy conservation in three communities (1 in each state) and what utilities can do to assist in removing barriers. | COG, State and Local Government, Utilities | bar: 2011 4th
61 |  |  | One jurisdiction establishes home energy loan program or other innovative municipal financing program for building retrofits. | Local Governments | [12 empty] | Yes | bar: 2010 2nd
62 |  |  | 35% of jurisdictions develop and implement Home Energy Loan Program. | Local Governments, COG, Maryland Clean Energy Center, State Energy Offices, Private Sector | [12 empty] | Yes | bar: 2012 1st
63 |  |  | 30% of jurisdictions, in cooperation with their state energy offices, promote or provide incentive programs to encourage purchase of new energy efficient applicances. | State or Local Governments, Utilities | [12 empty] | Yes | bar: 2011 3rd
64 |  |  | 30% of jurisdictions partner with utilities to implement smart grid technology. | State or Local Governments, Utilities | [12 empty] | Yes | bar: 2011 3rd
65
66 |  | Building Retrofits
67 |  |  | 1,500 residential units retrofitted annually. | Community, State Energy Offices, Utilities | [12 empty] | Yes | bar: 2010 4th; 2011 4th; 2012 4th
69 |  |  | 250 commercial buildings retrofitted annually. | Community, State Energy Offices, Utilities | [12 empty] | Yes | bar: 2010 4th; 2011 4th; 2012 4th
72
73 |  | Green Purchasing Policies
74 |  |  | 60% of jurisdictions adopt green purchasing policies. | Local Governments, COG | [12 empty] | Yes | bar: 2011 2nd
75 |  |  | 50% of jurisdictions participate in a regional/subregional cooperative green purchasing program. | Local Governments, COG | [12 empty] | Yes | bar: 2012 1st
Note: (a) Recommendations and Performance Measures are intended for those jurisdictions where implementing authority exists.
76 |  | B. Renewable Energy
77
78 |  | Renewable Energy Purchases
79 |  |  | 100% of jurisdictions purchase or consume 10 percent renewable energy. | Local Governments, Power Purchase Groups, COG, Utilities, Green Power Providers | [12 empty] | Yes | bar: 2012 1st
80 |  |  | 50% of jurisdictions, in collaboration with state energy offices, assist or provide incentives for consumer purchase of renewable energy (e.g., Montgomery County Clean Energy Rewards Program). | Local Governments, State Energy Offices | bar: 2012 1st
81 |  |  | 25% of utility consumers purchase a portion of their energy consumption from renewable energy. | Consumers, Utilities, Green Power Providers | [12 empty] | Yes | bar: 2012 1st
83
84 |  | Renewable and Cleaner Energy System Installations
84a |  |  | Evaluate the economic and environmental benefits of integrated community energy solutions, including focus on promoting effective use of waste heat and combined heat/power solutions in the region. | COG, Local Governments, Expert Task Force, Consultant | bar: 2011 2nd
84b |  |  | At least two jurisdictions evaluate potential for including integrated community energy solutions in development projects. | Local Governments, NVRC, MCEC, State Governments, Private Sector | bar: 2011 3rd; 2012 2nd
85 |  |  | Develop a regional inventory of renewable and cleaner energy capacity and production, including solar, geothermal, district heating/cooling, wind, and biofuels | Local Governments, COG, Utilities | bar: 2010 4th; 2011 4th; 2012 4th
86 |  |  | 75% of local governments deploy renewable energy technology. | Local Governments, Green Power Companies | [12 empty] | Yes | bar: 2011 3rd
87 |  |  | Implement one regional pilot project promoting a renewable energy park. | Federal, State, and Local Government, Private Sector | [12 empty] | Yes | bar: 2012 2nd
88 |  |  | 1000 residential, commercial, or government buildings have renewable energy systems installed. | Federal, State, and Local Government, Private Sector | [12 empty] | Yes | bar: 2010 4th
89 |  |  | 5000 residential, commercial, or government buildings have renewable energy systems installed. | Federal, State, and Local Government, Private Sector | [12 empty] | Yes | bar: 2011 4th
90 |  |  | 10000 residential, commercial, or government buildings have renewable energy systems installed. | Federal, State, and Local Government, Private Sector | [12 empty] | Yes | bar: 2012 4th
91
92 |  | Financing and Supporting Renewable and Cleaner Energy
93 |  |  | Develop a matrix of options for financing renewable and cleaner energy projects. | COG, Local Governments, Board of Trade | bar: 2010 3rd
94 |  |  | All state and local jurisdictions remove barriers to implementing renewable and cleaner energy by the private sector, e.g., solar panels. | Federal, State, and Local Government | bar: 2012 4th
95
96 |  | C. Other Sectors
97 |  |  | Increase diversion rate (percent of waste diverted from landfills/incinerators) from 30% to 40%b. | Local Governments, Residents, Businesses | [12 empty] | Yes | bar: 2012 3rd
98 |  |  | 100% of wastewater facilities identify best practices to reduce methane and biosolids from wastewater treatment and evaluate feasibility through cost/benefit analysis of potential actions. | Wastewater Utilities, Water Resources Technical Committee | bar: 2012 1st
|  | Note: (a) Recommendations and Performance Measures are intended for those jurisdictions where implementing authority exists. |  | (b) Region Forward goals will be tracked and reported every other year by COG Dept of Community Planning
99 | III. Transportation and Land Use
100
101 | A. TPB Work Program Activities
102
103 |  | Prepare Greenhouse Gas Emission Inventories
104 |  |  | Prepare regional transportation greenhouse gas inventories and forecasts for all milestone years. | TPB | bar: 2010 1st
105
106 |  | Evaluate Greenhouse Gas Emission Reduction Measures
107 |  |  | Perform cost-effectiveness and cost-benefit analyses of transportation and land use greenhouse gas emission reduction measures (e.g., fuel efficiency, alternative fuels, travel efficiency including land use). | TPB, CEEPC | bar: 2010 1st
108
109 |  | Identify Emission Reduction Strategies
110 |  |  | Identify cost effective strategies for implementation. | TPB, CEEPC | bar: 2010 2nd
111
112 |  | Conduct Metropolitan Planning Process
113 |  |  | Conduct continued regional metropolitan planning process that includes consideration of greenhouse gas emissions; continue ongoing activities and incorporate MPO planning requirements from pending federal climate change and transportation legislation once enacted. | TPB | bar: 2010 2nd
114
115 | B. Local and Regional Strategies
116
117 |  | Green Fleet Policy
118 |  |  | COG adopts green fleet policy that includes accelerated implementation of federal CAFE Standards/GHG emission standards for local government fleets. | COG, Local Governments | bar: 2011 4th
119 |  |  | 30% of jurisdictions have developed and implemented a green fleet policy. | Local Governments | [12 empty] | Yes | bar: 2011 4th
120 |  |  | 50% of jurisdictions have developed and implemented a green fleet policy. | Local Governments | [12 empty] | Yes | bar: 2012 4th
121 |  |  | 50% of jurisdictions implement alternative fuel infrastructure projects needed to support alternative fuel vehicle technology implementation (e.g., natural gas, biofuel, hydrogen, electricity). | Local Governments, COG, Private Sector | [12 empty] | Yes | bar: 2012 2nd
122
123 |  | VMT/Capita Reduction Programs
124 |  |  | 100% of jurisdictions implement programs to meet the Region Forward target to reduce VMT per capita(b). | State and Local Governments, Private Sector | [12 empty] | Yes | bar: 2012 1st
125 |  |  | 60-70% of jurisdictions implement parking policies that reduce VMT. | Local Governments | [12 empty] | Yes | bar: 2012 2nd
126 |  |  | 60% of jurisdictions adopt best practices for traffic engineering improvements and road management to reduce greenhouse gases. | Local Governments, DOTs | [12 empty] | Yes | bar: 2011 3rd
|  | Note: (a) Recommendations and Performance Measures are intended for those jurisdictions where implementing authority exists. |  | (b) Region Forward goals will be tracked and reported every other year by COG Dept of Community Planning
127 |  | Promote Use of Transit and Multimodal Options
128 |  |  | 100% of transit agencies promote the increased use of existing transit capacity. | Transit Agencies, COG | [12 empty] | Yes | bar: 2011 3rd
129 |  |  | 80% of jurisdictions implement programs to expand commuter options (telework, car sharing, bicycle/pedestrian, financial incentives). | Local Governments, COG | [12 empty] | Yes | bar: 2011 1st
130 |  |  | 100% of jurisdictions develop plans to meet the Region Forward target to increase the rate of construction of bike and pedestrian facilities included in the Transportation Planning Board’s plan(b). | State and Local Governments | [12 empty] | Yes | bar: 2011 1st
131 |  |  | 100% of jurisdictions implement programs to meet the Region Forward target to increase the share of walk, bike, and transit trips(b). | State and Local Governments, Private Sector | [12 empty] | Yes | bar: 2011 2nd
132 |  |  | 100% of jurisdictions implement programs to meet the Region Forward target of ensuring that all Regional Activity Centers will have transit accessibility (bus or rail)(b). | State and Local Governments, Transit Agencies, Private Sector | [12 empty] | Yes | bar: 2012 4th
133 |  |  | 100% of jurisdictions develop plans to meet the Region Forward target to direct transportation investments that link Regional Activity Centers(b). | State and Local Governments, Transit Agencies, Private Sector | bar: 2012 1st
134
135 |  | Increase Green Infrastructure
136 |  |  | 75% of local governments prepare plans to increase tree canopy. | COG, Local Governments, USFS, State Forestry Offices, Private Landowners | [12 empty] | Yes | bar: 2011 2nd
137 |  |  | Prepare regional plan to increase tree canopy. | COG, Local Governments, USFS, State Forestry Offices, Private Landowners | [12 empty] | Yes | bar: 2012 1st
137a |  |  | Develop local and regional plans to increase food production and distribution in the region. | COG, Local Governments, Private Sector | bar: 2012 1st
138 |  |  | Develop plans to meet the Region Forward target to maintain more than 450,000 acres of agriculture land in farms(b). | State and Local Governments, MDPC | [12 empty] | Yes | bar: 2012 2nd
139 |  |  | 100% of jurisdictions develop plans to meet the Region Forward target to identify, conserve, and enhance a network of protected open spaces, parks, and green infrastructure(b). | State and Local Government, National Park Service, Private Landowners | [12 empty] | Yes | bar: 2011 3rd
140
141 |  | Land Use and Comprehensive Planning
142 |  |  | 80% of jurisdictions promote transit-oriented development/Concentrate future growth in Regional Activity Centers. | Local Governments, Planning Directors, Metropolitan Development Policy Committee | [12 empty] | Yes | bar: 2011 3rd
143 |  |  | 100% of jurisdictions meet the Region Forward targets for growth (75% of commercial square feet and 50% of households) occurring in Regional Activity Centers(b). | Local Governments, Planning Directors, Metropolitan Development Policy Committee | [12 empty] | Yes | bar: 2011 4th; 2012 4th
144 |  |  | Develop methodologies to assist local governments consider greenhouse gas emission impacts of land use and transportation decisions in local comprehensive planning and project reviews. | COG, EPA | bar: 2011 2nd
145 |  |  | 50% of jurisdictions integrate considerations of greenhouse gas emission impacts of land use and transportation decisions into comprehensive planning and project reviews. | Local Governments | [12 empty] | Yes | bar: 2012 1st
146
147 |  | Reduce Idling
148 |  |  | 100% of jurisdictions have idling regulations and enforce them, as reflected through review of citations and education/outreach. | Local Governments | [12 empty] | Yes | bar: 2010 2nd
|  | Note: (a) Recommendations and Performance Measures are intended for those jurisdictions where implementing authority exists. |  | (b) Region Forward goals will be tracked and reported every other year by COG Dept of Community Planning
152 | IV. Adaptation
153 |  |  | Research climate change and adaptation strategies, including lessons learned from other regions and regional adaptation options. | COG, Universities, Private Sector, State, Local, and Federal Government | bar: 2010 2nd
154 |  |  | Hold adaptation workshops (topics to address: sector-specific, results of research findings and recommendation, potential regional adaptation strategies). | COG, Universities, Private Sector, State, Local, and Federal Government | bar: 2010 2nd; 2011 1st; 2011 4th; 2012 2nd
155 |  |  | Evaluate complete impact (e.g., environmental, financial, other) of climate change on one or more sectors (such as water, wastewater, air, energy, public health, public safety). | COG, Universities, Private Sector, State, Local, and Federal Government | bar: 2010 4th
156 |  |  | Develop draft regional adaptation plan. | COG, Universities, Private Sector, State, Local, and Federal Government | bar: 2012 2nd
157 | V. Outreach & Education
158 |  | Regional Climate and Energy Public Education Campaign
159 |  |  | Develop partnerships to fund and implement a regional climate and energy public education campaign. | COG, Universities, Local Governments, Utilities, State Energy Offices, Media, Foundations | [12 empty] | Yes | bar: 2010 1st
160 |  |  | Conduct stakeholder identification and analysis for outreach campaign, implement regional survey to assess awareness. | COG, Universities, Local Governments, Utilities, State Energy Offices, Media, Foundations | bar: 2010 2nd
161 |  |  | Develop targeted public education campaign materials, including press packs and social marketing campaign materials. | COG, Universities, Local Governments, Utilities, State Energy Offices, Media, Foundations | [12 empty] | Yes | bar: 2010 3rd
162 |  |  | Implement regional pilot public outreach and education campaign. | COG, Universities, Local Governments, Utilities, State Energy Offices, Media, Foundations | [12 empty] | Yes | bar: 2011 1st
163 |  |  | Implement regional public outreach and education campaign. | COG, Universities, Local Governments, Utilities, State Energy Offices, Media, Foundations | [12 empty] | Yes | bar: 2011 4th
Note: (a) Recommendations and Performance Measures are intended for those jurisdictions where implementing authority exists.
Acronyms Used in this document:
CEEPC – COG’s Climate, Energy and Environment Policy Committee
COG – Metropolitan Washington Council of Governments
EAC – COG’s Energy Advisory Committee (supporting technical committee to CEEPC)
EPA – U.S. Environmental Protection Agency
ESCOs – Energy Service Companies (perform energy audits and retrofits, usually with financial guarantees)
ICLEI – International Association of Local Governments for Sustainability
IGBG – COG’s Intergovernmental Green Building Group (supporting technical committee to CEEPC)
LEED – U.S. Green Building Council’s green building standard “Leadership in Environmental and Energy Design”
LEED-EB – LEED standard for existing buildings.
LEED-ND – LEED standard for neighborhood development
MATOC – Metropolitan Area Transportation Operations Coordination program (MATOC is a regional program to enhance the availability of real-time transportation information)
MDPC – COG’s Metropolitan Development Policy Committee (policy advisory committee to COG Board of Directors; COG’s lead committee for implementation of Greater Washington 2050 report and compact)
MPO – Metropolitan Planning Organization as defined in federal transportation law. The TPB (see below) is the MPO for the National Capital Region.
RESNET – Residential Energy Services Network; formed by the National Association of State Energy Officials and Energy Rated Homes of America to develop a national market for home energy rating systems and energy efficient mortgages.
TPB – National Capital Region Transportation Planning Board (regional transportation metropolitan planning agency housed at COG)
WRI – World Resources Institute