## Summary
FY 2012 TPB TIGER Grant Application - Cost and Schedule
[7 empty] | CY 2013 |  |  |  | CY 2014 |  |  |  | CY 2015 |  |  |  | CY 2016
[5 empty] | FY2013 |  |  |  | FY 2014 |  |  |  | FY 2015 |  |  |  | FY 2016 |  |  |  | FY 2017 |  |  |  | TOTALS
[5 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Total Budget | TIGER | Local | Match
District Of Columbia
Fort Totten / 1st Place-Galloway Road Access Improvement Project | 4171050 | 3336840 | 834210 | 20% | FY2013 3Q: 258750; FY2013 4Q: 258750; FY 2014 1Q: 0; FY 2014 2Q: 1216336.485; FY 2014 3Q: 1216336.485; FY 2014 4Q: 1220877.03 | 4171050
Maryland
Forest Glen Metrorail Access Project | 15555000 | 10444000 | 5111000 | 32.86% |  |  | 105000 | 105000 | 412833.3333 | 412833.3333 | 412833.3333 | 912833.3333 | 496924.2424 | 496924.2424 | 744424.2424 | 879424.2424 | 946924.2424 | 946924.2424 | 904840.9091 | 1765674.2424 | 1926924.2424 | 2291299.2424 | 1793382.5758 |  | 15555000
Pedestrian Safety Measures for the New Carrollton Metrorail Station | 575423.775 | 402796.6425 | 172627.1325 | 30% | FY 2014 1Q: 51750; FY 2014 2Q: 72450; FY 2014 3Q: 259249.3875; FY 2014 4Q: 150574.3875; FY 2015 1Q: 41400 | 575423.775
Rosslyn Circle Crossing | 4020000 | 750000 | 3270000 | 81.34% | FY2013 3Q: 68600; FY 2014 1Q: 65000; FY 2014 2Q: 1376000; FY 2014 3Q: 1000000; FY 2014 4Q: 1510400 | 4020000
West Hyattsville Metrorail Station Access Improvements | 710250 | 542750 | 167500 | 23.58% | FY 2014 2Q: 37500; FY 2014 3Q: 257583.3333; FY 2014 4Q: 267583.3333; FY 2015 1Q: 147583.3333 | 710250
Virginia
Arlington Army Navy Drive Multimodal Access Improvement Project | 6838879 | 4215983 | 2622896 | 38.35% | FY2013 1Q: 483928.74; FY2013 2Q: 31050; FY2013 3Q: 1580975.1787; FY2013 4Q: 1580975.1787; FY 2014 1Q: 1580975.1787; FY 2014 2Q: 1580975.1787 | 6838879.455
Bicycle Lockers at VRE Stations | 283600.35 | 226880.28 | 56720.07 | 20% | FY 2014 3Q: 65555; FY 2014 4Q: 108655; FY 2015 1Q: 56905; FY 2015 2Q: 44505; FY 2015 3Q: 7980 | 283600
TOTAL Project Implementation Cost | 32154203.125 | 19919249.9225 | 12234953.2025 | 38.05% | 483928.74 | 31050 | 2013325.1787 | 1944725.1787 | 2110558.5121 | 4696094.9971 | 3211557.5392 | 4170923.0842 | 742812.5758 | 541429.2424 | 752404.2424 | 879424.2424 | 946924.2424 | 946924.2424 | 904840.9091 | 1765674.2424 | 1926924.2424 | 2291299.2424 | 1793382.5758 |  | 31639224.49
Jobs Created/Retained |  |  |  |  | 6.2911 | 0.40365 | 26.1733 | 25.2815 | 27.4373 | 61.0493 | 41.7503 | 54.2221 | 9.6566 | 7.0386 | 9.7813 | 11.4325 | 12.31 | 12.31 | 11.7629 | 22.9538 | 25.05 | 29.7869 | 23.314 |  | 411.3103
Direct, On-Project Jobs |  |  |  |  | 4.0263 | 0.25834 | 16.7509 | 16.1801 | 17.5599 | 39.0715 | 26.7202 | 34.7021 | 6.1802 | 4.5047 | 6.26 | 7.3168 | 7.8784 | 7.8784 | 7.5283 | 14.6904 | 16.032 | 19.0636 | 14.921 |  | 263.2386
Induced Jobs |  |  |  |  | 2.2648 | 0.14531 | 9.4224 | 9.1013 | 9.8774 | 21.9777 | 15.0301 | 19.5199 | 3.4764 | 2.5339 | 3.5213 | 4.1157 | 4.4316 | 4.4316 | 4.2347 | 8.2634 | 9.018 | 10.7233 | 8.393 |  | 148.0717

## DC Ftotten
FY 2012 TPB TIGER Grant Application - Cost and Schedule | [7 empty] | 2013
[6 empty] | FY 2013 |  |  |  | FY 2013
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
Fort Totten Station Access
Included in TIGER Request
1. Final Design & Engineering | Design | DDOT | Contractor | 500000 | TIGER
Complete final design (30% to 100%) and engineering for project. | [5 empty] | FY 2013 3Q: 250000; FY 2013 4Q: 250000
2. Construction | Construction | DDOT | Contractor | 3530000 | TIGER
2.1 1st Place NE Section
Excavation, Milling, grading, curb and gutter, asphalt, pavement markings, catch basins, street lights | Procure | DDOT | Contractor | 752641 |  | FY 2013 2Q: 250880.3333; FY 2013 3Q: 250880.3333; FY 2013 4Q: 250880.3333
2.2 WMATA property Section
Excavation, Milling, grading, curb and gutter, asphalt, pavement markings, catch basins, street lights, rain garden | Procure | DDOT | Contractor | 1711513 |  | FY 2013 2Q: 570504.3333; FY 2013 3Q: 570504.3333; FY 2013 4Q: 570504.3333
2.3 Pedestrian Plaza
Pavers, secure bike parking, landscape | Procure | DDOT | Contractor | 622380 |  | FY 2013 2Q: 207460; FY 2013 3Q: 207460; FY 2013 4Q: 207460
2.4 Galloway Street NE Section
Excavation, Milling, grading, curb and gutter, asphalt, pavement markings, retaining wall | Procure | DDOT | Contractor | 439079 |  | FY 2013 2Q: 146359.6667; FY 2013 3Q: 146359.6667; FY 2013 4Q: 146359.6667
Total Construction Costs (not rounded) |  |  |  | 3525613 |  | FY 2013 4Q: 4387
Project Implementation Cost |  |  |  | 4030000 |  |  |  | 250000 | 250000 | 0 | 1175204.3333 | 1175204.3333 | 1179591.3333
COG PM Costs (3.5%) |  |  |  | 141050 |  |  |  | 8750 | 8750 | 0 | 41132.1517 | 41132.1517 | 41285.6967
TOTAL Project Implementation Cost |  |  |  | 4171050 |  |  |  | 258750 | 258750 | 0 | 1216336.485 | 1216336.485 | 1220877.03 | 4171050
Total TIGER Funds |  |  |  | 3336840 | 80%
Total Other Funds (% match) |  |  |  | 834210 | 20%
0
0

## MC F Glen
Forest Glen Pedestrian Passageway | [7 empty] | CY 2013 |  |  |  | CY 2014 |  |  |  | CY 2015 |  |  |  | CY 2016
FY 2012 TPB TIGER Grant Application - Cost and Schedule | [5 empty] | FY 2013 |  |  |  | FY 2014 |  |  |  | FY 2015 |  |  |  | FY 2016 |  |  |  | FY 2017
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
Forest Glen Pedestrian Passageway under
Georgia Avenue
1. Planning | Design | County | County | 210000 | TIGER
Management and Review (Mont. County) |  |  |  | 50000 |  | FY 2013 3Q: 25000; FY 2013 4Q: 25000 | 50000
Agency (SHA and WMATA) Review |  |  |  | 10000 |  | FY 2013 3Q: 5000; FY 2013 4Q: 5000 | 10000
Planning/NEPA Documentation |  |  |  | 150000 |  | FY 2013 3Q: 75000; FY 2013 4Q: 75000 | 150000
2. Final Design and Engineering | Design | County | County | 2815000
Management and Review (Mont. County) |  |  |  | 150000 |  | FY 2014 1Q: 37500; FY 2014 2Q: 37500; FY 2014 3Q: 37500; FY 2014 4Q: 37500 | 150000
Management and Administration (MWCOG) |  |  |  | 530000 | [5 empty] | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 | 35333.3333 |  | 530000
Agency (SHA and WMATA) Review |  |  |  | 100000 |  | FY 2014 1Q: 25000; FY 2014 2Q: 25000; FY 2014 3Q: 25000; FY 2014 4Q: 25000 | 100000
Final design and engineering for project |  |  |  | 1260000 |  | FY 2014 1Q: 315000; FY 2014 2Q: 315000; FY 2014 3Q: 315000; FY 2014 4Q: 315000 | 1260000
Construction Management and Inspection (Mont. County) |  |  |  | 775000 |  | FY 2015 1Q: 70454.5455; FY 2015 2Q: 70454.5455; FY 2015 3Q: 70454.5455; FY 2015 4Q: 70454.5455; FY 2016 1Q: 70454.5455; FY 2016 2Q: 70454.5455; FY 2016 3Q: 70454.5455; FY 2016 4Q: 70454.5455; FY 2017 1Q: 70454.5455; FY 2017 2Q: 70454.5455; FY 2017 3Q: 70454.5455 | 775000
3. Land Acquisition | Acquisition | County | County | 500000
Acquire required Right-of-Way, Easements |  |  |  | 500000 |  | FY 2014 4Q: 500000 | 500000
4. Construct Pedestrian Passageway | Construction | County | Contractor | 11530000
Utility Relocation |  |  |  | 585000 |  | FY 2015 1Q: 292500; FY 2015 2Q: 292500 | 585000
Install Support of Excavation |  |  |  | 2160000 |  | FY 2015 3Q: 540000; FY 2015 4Q: 540000; FY 2016 1Q: 540000; FY 2016 2Q: 540000 | 2160000
Excavate and Install Temporary Bridge |  |  |  | 810000 |  | FY 2015 4Q: 135000; FY 2016 1Q: 202500; FY 2016 2Q: 202500; FY 2016 3Q: 202500; FY 2016 4Q: 67500 | 810000
Construct Ped. Passageway and Station Tie-In |  |  |  | 5975000 |  | FY 2016 3Q: 497916.6667; FY 2016 4Q: 1493750; FY 2017 1Q: 1493750; FY 2017 2Q: 1493750; FY 2017 3Q: 995833.3333 | 5975000
Maintenance of Traffic |  |  |  | 1085000 |  | FY 2015 1Q: 98636.3636; FY 2015 2Q: 98636.3636; FY 2015 3Q: 98636.3636; FY 2015 4Q: 98636.3636; FY 2016 1Q: 98636.3636; FY 2016 2Q: 98636.3636; FY 2016 3Q: 98636.3636; FY 2016 4Q: 98636.3636; FY 2017 1Q: 98636.3636; FY 2017 2Q: 98636.3636; FY 2017 3Q: 98636.3636 | 1085000
Conduct Roadway Restoration |  |  |  | 915000 |  | FY 2017 1Q: 228750; FY 2017 2Q: 343125; FY 2017 3Q: 343125 | 915000
5. Bike Share Stations | Construction | County |  | 500000
Construct Bike Share Stations |  |  |  | 500000 |  | FY 2017 2Q: 250000; FY 2017 3Q: 250000 | 500000
TOTAL Project Implementation Cost |  |  |  | 15555000 |  | 0 | 0 | 105000 | 105000 | 412833.3333 | 412833.3333 | 412833.3333 | 912833.3333 | 496924.2424 | 496924.2424 | 744424.2424 | 879424.2424 | 946924.2424 | 946924.2424 | 904840.9091 | 1765674.2424 | 1926924.2424 | 2291299.2424 | 1793382.5758 |  | 15555000
[11 empty] | 1035666.6667 |  |  |  | 2319515.1515 |  |  |  | 3517696.9697 |  |  |  | 6888738.6364
Total TIGER Funds |  |  |  | 10444000 | 67.14%
Total Other Funds (% match) |  |  |  | 5111000 | 32.86%

## PG NewC
FY 2012 TPB TIGER Grant Application - Cost and Schedule | [7 empty] | CY 2013
[6 empty] | FY 2013 |  |  |  | FY 2014
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
New Carrollton Safety Measures for the New Carrollton Metro Station
2. Construct Pedestrian Crossings |  |  |  | 555965 | TIGER | [8 empty] | SUM
2.4 Install six new lights along roadway for Ellin Road |  |  |  | 70965 | 49675.5 | FY 2014 1Q: 35482.5; FY 2014 2Q: 35482.5 | 70965
2.5 Upgrade existing geometry and signal to the latest ADA standards for pedestrian and overall safety
at Garden City Drive at Corporate Place |  |  |  | 270000 | 189000 | FY 2013 3Q: 50000; FY 2013 4Q: 50000; FY 2014 1Q: 100000; FY 2014 2Q: 70000 | 270000
2.6 Install pedestrian walkway on Ellin Road From Veterans Parkway to Emerson Place |  |  |  | 140000 | 98000 | FY 2013 4Q: 20000; FY 2014 1Q: 40000; FY 2014 2Q: 40000; FY 2014 3Q: 40000 | 140000
2.8 Provide 10 trash receptacles |  |  |  | 15000 | 10500 | FY 2014 1Q: 15000 | 15000
2.9 Provide 10 benches |  |  |  | 15000 | 10500 | FY 2014 1Q: 15000 | 15000
3.0 Consolidate Bus Stops on Annapolis Road (WMATA) |  |  |  | 15000 | 10500 | FY 2014 1Q: 15000 | 15000
3.1 Move Bus Stop closer to intersection of Annapolis Road and 85th Ave |  |  |  | 15000 | 10500 | FY 2014 1Q: 15000 | 15000
3.2 Move Bus Stop close to Intersection of Annapolis Road and Riverdale Road |  |  |  | 15000 | 10500 | FY 2014 1Q: 15000 | 15000
Project Construction Cost |  |  |  | 555965 | 389175.5
COG PM Costs |  |  |  | 19458.775 | 13621.1425 |  |  | 1750 | 2450 | 8766.8875 | 5091.8875 | 1400 |  | 19458.775
TOTAL Project Implementation Cost (inc COG PM) |  |  |  | 575423.775 | 402796.6425 |  |  | 51750 | 72450 | 259249.3875 | 150574.3875 | 41400 |  | 575423.775
Total TIGER request |  |  |  | 402796.6425 | 70% | FY 2014 2Q: 534023.775
Total Other Funds |  |  |  | 172627.1325 | 30%
[15 empty] | 0 | 0 | 0
[15 empty] | 0 |  | 0

## Arl RCC
FY 2012 TPB TIGER Grant Application - Cost and Schedule |  |  |  |  | CY 2012 |  |  |  | CY 2013 |  |  |  | CY 2014
[7 empty] | FY 2013 |  |  |  | FY 2014
[7 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project (By Study Corridor) | Activity | Lead Agency | Workforce | Budget | Existing or New Infrastructure | Funding Source
Rosslyn Circle Crossing
RTSP Grant
FHWA / RSTP (80%) |  |  |  | 800000
State Match (20%) |  |  |  | 200000
1. Planning | Design | County | Contractor | 1068600 | Ex. / New
Arl Co Management and Review | planning |  |  | 60000 |  | FHWA - | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
VDOT / FHWA Agency Review | planning |  |  | 40000 |  | FHWA - | FY 2013 1Q: 10000; FY 2013 3Q: 10000; FY 2014 1Q: 10000; FY 2014 3Q: 10000
Planning/NEPA Documentation | planning |  |  | 60500 |  | FHWA - | FY 2013 1Q: 60500; FY 2013 2Q: (Tasks completed 2010)
25% Engineering | Design |  |  | 99000 |  | FHWA - | FY 2013 1Q: 99000; FY 2013 2Q: (Tasks completed 2011)
50% Engineering | Design |  |  | 153000 |  | FHWA - | FY 2013 1Q: 153000; FY 2013 2Q: (Tasks completed 2011)
Public Involvement | Design |  |  | 37000 |  | FHWA - | FY 2013 1Q: 27000; FY 2013 3Q: 10000
60% Engineering | Design |  |  | 119000 |  | FHWA - | FY 2013 1Q: 119000
Structure and Bridge Modifications | Design |  |  | 86600 |  | FHWA - | FY 2013 2Q: 49000; FY 2013 3Q: 37600
Structure and Bridge Modifications Ph II | Design |  |  | 183500 |  | FHWA - | FY 2013 3Q: 114900
[6 empty] | Dev. Contribution / Tiger | FY 2013 3Q: 68600
VDOT Management and Administration | Design |  |  | 70000 |  | FHWA - | FY 2013 4Q: 70000
Final design and engineering for project | Design |  |  | 50000 |  | FHWA - | FY 2013 4Q: 50000
Bid Preparation | Design |  |  | 25000 |  | FHWA - | FY 2014 1Q: 25000
Construction Management and Inspection | Design |  |  | 60000 |  | FHWA - | FY 2014 2Q: 20000; FY 2014 3Q: 20000; FY 2014 4Q: 20000
Design Contingency / Final VDOT Revisions | Design |  |  | 25000 |  | FHWA - | FY 2014 4Q: 25000
3. Land Acquisition | Acquisition | County | Contractor | 45000 | Ex. / New
Acquire required Right-of-Way, Easements | ROW |  |  | 45000 |  | Dev. Contribution / Tiger | FY 2014 1Q: 45000
4. Construct trail, intersection and sidewalk upgrades | Construction | County | Contractor | 3906400 | Ex. / New
VDOT Agency Inspection | Construction |  |  | 30000 |  | Dev. Contribution / Tiger | FY 2014 1Q: 20000; FY 2014 4Q: 10000
Utility Relocation | Construction |  |  | 40000 |  | Dev. Contribution / Tiger | FY 2014 2Q: 40000
Construct Ped and Bike access Improv. | Construction |  |  | 3336000 |  | Dev. Contribution / Tiger | FY 2014 2Q: 1336000; FY 2014 3Q: 1000000; FY 2014 4Q: 1000000
15% contingency and MWCOG PM fee (of const. cost) | Construction |  |  | 500400 |  | Dev. Contribution / Tiger | FY 2014 4Q: 500400
TOTAL Project Implementation Cost |  |  |  | 4020000 |  |  | 0 | 0 | 68600 | 0 | 65000 | 1376000 | 1000000 | 1510400 | 4020000
Developer Contribution |  |  |  | 3270000
Total Required TIGER Funds |  |  |  | 750000
TOTAL Funding Required |  |  |  | 4020000

## PG WH
FY 2012 TPB TIGER Grant Application - Cost and Schedule
CY 2014
[6 empty] | FY 2014 |  |  |  | FY 2015
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
West Hyattsville Access Improvments - Project Start Date - January 2012
NOT FUNDED BY TIGER - Included in Local Matching
1. Planning, Design & Engineering | Design | County | Consultant |  | County
| Jamestown Road Sidewalk Design |  |  | 37500 |  | FY 2014 2Q: 37500
(note: Design costs are not a part of Tiger request)
Construction - Start Date - September 2013 | Construction | County | Contractor |  | TIGER 80%
West Hyattsville Project Access Improvements
| Jamestown Road Sidewalk Construction |  |  | 250000 | 200000 | FY 2014 3Q: 50000; FY 2014 4Q: 100000; FY 2015 1Q: 100000
| WMATA Secure Bike Station |  |  | 400000 | 320000 | FY 2014 3Q: 200000; FY 2014 4Q: 160000; FY 2015 1Q: 40000
Project Implementation Cost |  |  |  | 687500 |  | FY 2014 3Q: 250000; FY 2014 4Q: 260000; FY 2015 1Q: 140000
Construction Costs |  |  |  | 650000 | 520000
Plus COG PM Costs (3.5%) |  |  |  | 22750 | 22750 | FY 2014 3Q: 7583.3333; FY 2014 4Q: 7583.3333; FY 2015 1Q: 7583.3333
TOTAL Project Construction Costs |  |  |  | 672750 | 542750 | FY 2014 2Q: 37500; FY 2014 3Q: 257583.3333; FY 2014 4Q: 267583.3333; FY 2015 1Q: 147583.3333
TOTAL Project Implementation Cost |  |  |  | 710250 |  | FY 2015 1Q: 710250
Total TIGER Funds |  |  |  | 542750 | 76.42%
Total Other Funds (% match) |  |  |  | 167500 | 23.58%

## Arl A-N
FY 2012 TPB TIGER Grant Application - Cost and Schedule | [7 empty] | CY 2013
[6 empty] | FY 2013 |  |  |  | FY 2014
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
Combined Pentagon / Pentagon City / Crystal City Access Improvement Project
1. Planning | NOT FUNDED BY TIGER - Included in Local Matching
Army Navy Drive | Planning
30% design |  | FHWA |  |  | FHWA | FY 2013 1Q: Finished as of FY 2011.
100% design and site coordination |  | Arlington |  |  | Arlington | FY 2013 3Q: Completed mid-FY2013
Bikesharing 5 initial stations | Planning
Plan station locations |  | Arlington |  |  | Arlington | FY 2013 1Q: To be completed FY2012
Obtain environmental clearance |  | Arlington |  |  | Arlington | FY 2013 1Q: To be completed FY2012
Bikesharing 5 additional stations | Planning
Plan station locations |  | Arlington |  |  | Arlington | FY 2013 1Q: To be completed FY2012
Obtain environmental clearance |  | Arlington |  |  | Arlington | FY 2013 1Q: To be completed FY2012
Total Planning Costs - all Local
2. Implementation |  |  |  | Overall | TIGER
Army Navy Drive Construction | Construction
Arlington portion |  |  |  | 2622896 | Arlington | FY 2013 3Q: 655724; FY 2013 4Q: 655724; FY 2014 1Q: 655724; FY 2014 2Q: 655724
TIGER portion |  |  |  | 3487153 | TIGER | FY 2013 3Q: 871788.25; FY 2013 4Q: 871788.25; FY 2014 1Q: 871788.25; FY 2014 2Q: 871788.25
Bikesharing 5 initial stations | Construction
Procurement |  |  |  | 233782 | TIGER | FY 2013 1Q: 233782
Installation |  |  |  | 15000 | TIGER | FY 2013 2Q: 15000
Bikesharing 5 additional stations | Construction
Procurement |  |  |  | 233782 | TIGER | FY 2013 1Q: 233782
Installation |  |  |  | 15000 | TIGER | FY 2013 2Q: 15000
Total Construction Costs |  |  |  | 6607613 | 4096720.06
COG PM (3.5%) of construction |  |  |  |  | 231266 | 16364.74 | 1050 | 53462.9288 | 53462.9288 | 53462.9288 | 53462.9288 |  | 231266.455
TOTAL |  |  |  | 6838879 | 4215983
TOTAL Project Implementation Cost |  |  |  | 6838879 |  | 483928.74 | 31050 | 1580975.1787 | 1580975.1787 | 1580975.1787 | 1580975.1787 |  | 6838879.455
Total TIGER Funds (%) |  |  |  | 4215983 | 61.65%
Total Other Funds (% match) |  |  |  | 2622896 | 38.35%

## VRE
FY 2012 TPB TIGER Grant Application - Cost and Schedule
CY 2013
[6 empty] | FY 2013 |  |  |  | FY 2014
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
VRE Bike Lockers
1. Install Bike Lockers |  |  |  | 283600.35 | TIGER
Install bike lockers at eight (8) locations
Broad Run
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration |  | VRE | VRE, MWCOG | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Rippon
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE, MWCOG | 5882.45 |  | FY 2013 3Q: 1470; FY 2013 4Q: 1470; FY 2014 1Q: 1470; FY 2014 2Q: 1473
Woodbridge
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE, MWCOG | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Manassas
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE, MWCOG | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Manassas Park
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE, MWCOG | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Rolling Rd.
Purchase lockers | Procure | VRE, Fairfax Co. | Manufacturer | 14500 |  | FY 2013 3Q: 7250; FY 2013 4Q: 7250
Prepare site | Construct | VRE, Fairfax Co. | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE, Fairfax Co. | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE, Fairfax Co. | VRE, Fairfax Co., MWCOG | 4462.5 |  | FY 2013 3Q: 1115; FY 2013 4Q: 1115; FY 2014 1Q: 1115; FY 2014 2Q: 1118
Lorton
Purchase lockers | Procure | VRE, Fairfax Co. | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE, Fairfax Co. | Contractor | 8200 |  | FY 2013 4Q: 4100; FY 2014 1Q: 4100
Install | Construct | VRE, Fairfax Co. | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE, Fairfax Co. | VRE, Fairfax Co., MWCOG | 4157.8 |  | FY 2013 3Q: 1040; FY 2013 4Q: 1040; FY 2014 1Q: 1040; FY 2014 2Q: 1038
Franconia-Springfield
Purchase lockers + bike racks | Procure | VRE, Fairfax Co. | Manufacturer | 19400 |  | FY 2013 3Q: 9700; FY 2013 4Q: 9700
Prepare site | Construct | VRE, Fairfax Co. | Contractor | 49700 |  | FY 2013 4Q: 16500; FY 2014 1Q: 16500; FY 2014 2Q: 16700
Install | Construct | VRE, Fairfax Co. | Contractor | 3000 |  | FY 2014 3Q: 3000
Permits, Inspection, Administration | Construct | VRE, Fairfax Co. | VRE, Fairfax Co., MWCOG | 24900.2 |  |  |  | 4980 | 4980 | 4980 | 4980 | 4980
TOTAL Project Implementation Cost |  |  |  | 283600.35 |  |  |  | 65555 | 108655 | 56905 | 44505 | 7980
Total TIGER Funds |  |  |  | 226880.28
Total Other Funds (% match) |  |  |  | 56720.07