## Sheet1
Draft 2015 Ozone NAAQS RR/MP Schedule (MWAQC-TAC, 2/11/2025)
| 2024 |  |  | 2025 | [11 empty] | 2026
Tasks | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Proposal to EPA - Milestone Years & Inv Dev Methodology | bar: 2024 Oct
EPA Response | bar: 2024 Dec
Point (EPA Modeling Inv from MARAMA) | bar: 2025 Feb to 2025 Apr
Non-Point (EPA Modeling Inv from MARAMA) | bar: 2025 Feb to 2025 Apr
MOVES Inputs from States | bar: 2025 Apr
QA/QC of States' MOVES Inputs & Dev. of Met Inputs | bar: 2025 Apr to 2025 May
Base Year 2017 Onroad Update | bar: 2025 Jun to 2025 Jul
Base Year 2017 Nonroad Update | bar: 2025 Jun
Attainment Year 2022 Onroad | bar: 2025 Aug to 2025 Sep
Attainment Year 2022 Nonroad | bar: 2025 Jul
Interim Year 2032 Onroad | bar: 2025 Oct
Interim Year 2032 Nonroad | bar: 2025 Sep
Final Year 2038 Onroad | bar: 2025 Nov
Final Year 2038 Nonroad | bar: 2025 Oct
Motor Vehicle Emissions Budgets | bar: 2025 Dec to 2026 Jan
Contingency Measures | bar: 2025 Mar to 2026 Jan
Plan Document Update | bar: 2025 Jun to 2026 Jan
EPA Review & Comment, Staff incorporates comments | bar: 2026 Feb to 2026 Mar
MWAQC Approval for Public Comments | bar: 2026 Apr to 2026 May
Public Hearings | bar: 2026 May to 2026 Aug
Address Public Comments & Finalize SIPs | bar: 2026 Aug to 2026 Sep
States Submit 2015 Ozone NAAQS RR/MP | bar: 2026 Oct to 2026 Dec
MWAQC-TAC & MWAQC Meeeting Dates in 2026
April: MWAQC-TAC-14, MWAQAC-Exec Com-15
May: MWAQC -15 (backup)
September: MWAQC-TAC-15, MWAQC-23