## Slide 1: National Capital Region Training and Exercise Plan
May 2013
Emergency Preparedness Council

## Slide 2: NCR TEP Purpose
Identifies training & exercise priorities
Identifies proposed training & exercises to address priorities (CY 2013 – 2014)
  ETOP led
  RESF/RPWG led
Identifies jurisdiction planned training & exercises
Provides a baseline for developing the ETOP PMP
Provides parameters for review and approval of PMPs submitted to ETOP

## Slide 3: NCR TEP Team
District of Columbia
  Vermecia Alsop, D.C. Homeland Security and Emergency Management Agency
  John Emminizer, D.C. Department of the Environment
  Jamie Quarrelles, D.C. Homeland Security and Emergency Management Agency
Maryland
  Kate Hession, Maryland Emergency Management Agency
  Kevin Molloy, Maryland Emergency Management Agency
  Phil Raum, Montgomery County Office of Emergency Management and Homeland Security
Virginia
  Aldo Davila, Fairfax County Office of Emergency Management
  James E. De Ford, Sr., Virginia State Police
  Jeffrey Driskill, City of Alexandria Office of Emergency Management
  Virgil Gray, Virginia Department of Emergency Management
  Joel A. Hendelman, Prince William County Office of Emergency Management
  Dave McKernan, Fairfax County Office of Emergency Management
  Susan Mongold, Virginia Department of Emergency Management
  Don Willis, Virginia Department of Emergency Management

## Slide 4: NCR TEP Process
December – April
Comprised a planning team (volunteer-based)
Informed NCR Stakeholders
Developed survey
Distributed the survey
  NCR State representatives
  Exercise and Training Officers
  Regional Emergency Support Function (RESF) representatives
  Regional Planning Working Group (RPWG) representatives
Gathered data from survey
Developed TEPW presentations
Conducted TEPWs
  1 TEPW per RESF/RPWG
  Each RESF/RPWG had designated TEP team
Developed and distributed TEPW minutes
TEP team provided input on what to include in draft TEP
Developed and reviewed multiple draft NCR TEPs
Distributed draft NCR TEP and all associated materials to NCR
Conducted a single, NCR-wide TEPW
Incorporated comments
Distributed final draft
Final

## Slide 5: TEPW Outcomes
April 9, 2013
Pleased with the overall process
  Actual NCR plan
  ETOP/ETOs will lead training & exercise efforts
  Engaging stakeholders/stakeholder buy-in
  Led by ETOP, not contractors
Less is more
  Training/exercises involve whole community
  Consolidate redundancies
  Training needs addressed by jurisdictions

## Slide 6: TEP Outcomes
Training – 64
Seminar – 18
Workshop – 2
Drill – 6
Tabletop – 9
Functional – 3
Full Scale – 8

## Slide 7: Next Steps
Re-identify priorities
  Universal needs
  Strategic plan
  Time frame
  Budget
  Ability to execute