## Slide 1
NCR Urban Areas Security Initiative Grants Update
12 November 2014
Grants Briefing to the NCR Emergency Preparedness Council

## Slide 2
FY 2014 UASI Awards
FY 2013 UASI Status
2015 Outlook
Agenda
Notes: 2

## Slide 3
FY2014 UASI award amount is $53,000,000
Most FY2014 sub-grant awards have been issued. Period of performance for sub-grant awards is 9/1/2014 – 5/31/2016
Working with sub-grantees and NCR PMO to resolve any out-standing issues with FY2014 projects
FY 2014 UASI
FY 2014 UASI period of performance is
September 1, 2014–August 31, 2016
Notes: 3

## Slide 4
FY2013 UASI award amount is $51,839,027
SAA issued awards in Sept. and Oct. Period of performance for sub-grant awards is 9/1/2013 – 5/31/2015
Currently approximately 28% of the award is expended, with 15% fully reimbursed to sub-grantees
FY 2013 UASI
FY 2013 UASI period of performance is
September 1, 2013–August 31, 2015
Notes: 4

## Slide 5: FY2013 UASI – Expires 08/31/2015
Chart: 
| Complete | Invoiced | On Order | Allocated to Projects
 | 7698103 | 6895125 | 16015864 | 21229935

## Slide 6
SAA has reviewed Q3 2014 and flagged any FY2013 UASI projects are facing significant delays or challenges
  Non-compliance: missing status reports, un-signed documents
  Under-spending, unrealistic or missing spending forecast
  Problems in project implementation
SAA will contact sub-grantees for corrective actions
  Reducing budget to account for under-spending
  Adjusting schedule to account for delays
  Addressing problems within a set timeframe
FY 2013 UASI – Project Progress Reporting
Q3 2014 sub-grant status reports were due to SAA on October 10, 2014
Notes: 6

## Slide 7
SAA is working with PMO to develop process for FY2015
  Identify capability needs
  Strategic process to address capability gaps
  Leadership input on priorities
  Proceed with developing potential 2015 projects ahead of FEMA grant application
FY 2015 application timeline will depend greatly on Congressional Appropriation
  A significant delay in appropriation may result in a compressed application timeframe
FY 2015 UASI Application
Notes: 7

## Slide 8
Charles Madden
DC HSEMA - Grants Division
202-724-6568
charles.madden@dc.gov
Questions?
Notes: 8