## ESF 1
Goal | Objectives | ESF 1 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Participate in development of NCR Strategic Plan for Voice. (Coordinating with SWIC Working Group - Statewide Interoperability Coordinators) | Oct 2013-Sept 2015 | RESF 1 w/SWICs
|  | Identify next generation backup communications for mass distribution to RESF-1 personnel to replace the current PTT devices that are being phased out | Oct 2013-Sept 2015 | RESF 1 w/SWICs
|  | Manage Radio Upgrades and maintain coordination of upgrades across jurisdictions | Oct 2013-Sept 2015 | RESF 1 w/SWICs
|  | Ensure communication interoperability across agencies | Oct 2013-Sept 2015 | RESF 1 w/SWICs
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Identify how RESF-1 can make greater use of NCRNet | Oct 2013-Sept 2015 | RESF 1 w/SWICs
| Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Continue to develop CCTV video sharing capability across NCRNet. | Oct 2013-Sept 2015 | RESF 1 w/SWICs
|  | Develop mobile video sharing capability | Oct 2013-Sept 2015 | RESF 1 w/SWICs
|  | Begin process to expand use of mobile video on DoT and other ESF-1 vehicles | Oct 2013-Sept 2015 | RESF 1
|  | Develop Video Sharing Conops, including any technical, legal & policy issues | Oct 2013-Sept 2015 | RESF 1 w/SWICs
|  | Identify bandwidth constraints on video sharing and explore options for increasing as appropriate | Oct 2013-Sept 2015 | RESF 1 w/SWICs
|  | Coordination & Collaboration with IT personnel over video sharing and mobile bandwidth | Oct 2013-Sept 2015 | RESF 1
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Maintain and enhance RITIS to provide additional and expanded capabilities for greater situational awareness | Oct 2013-Sept 2015 | RESF 1
|  | Explore potential for RITIS interface for WebEOC feeds, additional data input capabilities, as well as training/exercise instances of RITIS | Oct 2013-Sept 2015 | RESF 1
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Maintain and enhance RITIS for greater public situational awareness via VJIC and other public facing interfaces | Oct 2013-Sept 2015 | RESF 1
| Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner. | Make Vehicle-Probe Project (VPP) Analysis Suite available to Fusion Centers and other public safety partners as a dashboard for RITIS | Oct 2013-Sept 2015 | RESF 1 w/ Fusion Centers
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Explore options for automated sharing of CAD data with ESF-1 agencies to accelerate alerts and response for transportation related incidents | Oct 2013-Sept 2015 | RESF 1
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Develop plans and agreements for use of rail and maritime infrastructure in evacuation and emergency logistics | Oct 2013-Sept 2015 | RESF 1
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Identify hazard (flood, earthquake, hurricane, etc.) prone critical transportation infrastructure areas and develop appropriate contingency plans | Oct 2013-Sept 2015 | RESF 1
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | Identify and implement RITIS Mirror Site for resiliency | Oct 2013-Sept 2015 | RESF 1
|  | Inventory RESF-1 Critical Systems and Identify unmet resiliency requirements | Oct 2013-Sept 2015 | RESF 1
|  | Ensure Region has appropriate backup power on all RETC traffic control points for proper traffic control during power outages, especially if evacuation is required under power outages | Oct 2013-Sept 2015 | RESF 1
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Continue to develop evacuation plans which are coordinated across jurisdictions. | Oct 2013-Sept 2015 | RESF 1 w/ RESF 5
|  | Foster participation in ETOP Evacuation and Re-entry Planning Course, Mass Care and Evacuation exercises, Utilities Failure Exercise, Rail Service Based exercise, Intermodal Exercise | Oct 2013-Sept 2015 | RESF 1 w/ ETOP
|  | Foster staff participation in IMT training, exercises, and operations | Oct 2013-Sept 2015 | RESF 1 w/ ETOP
|  | Increase Emergency Management training opportunities for ESF-1 partners | Oct 2013-Sept 2015 | RESF 1 w/ ETOP
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | Coordinate with law enforcement sharing infrastructure for LPR and Traffic Cameras | Oct 2013-Sept 2015 | RESF 1 w/ RESF 13
|  | Provide personal radiation monitors for appropriate ESF-1 personnel and vehicles | Oct 2013-Sept 2015 | RESF 1
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | Ensure/Enhance RESF-1 input to PIOs regarding transportation messaging for inclusion in general emergency public outreach | Oct 2013-Sept 2015 | RESF 1 w / RESF 15
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
| Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region. | Develop plans, exercise plans, purchase necessary resources, train staff, coordinate with support agencies | Oct 2013-Sept 2015 | RESF 1 w/RESF 5
|  | Conduct NCR Emergency Evacuation Transportation Seminar/Trainings | Oct 2013-Sept 2015 | RESF 1 w/ ETOP + RESF 5
|  | Ensure appropriate traffic equipment is available in case of evacuation (e.g. Evacuation equipment trailers or stockpiles) | Oct 2013-Sept 2015 | RESF 1
|  | Coordinate with other entities on multifunctional exercises | Oct 2013-Sept 2015 | RESF 1 w/ ETOP
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues impacting transportation coordination. | Oct 2013-Sept 2015 | RESF 1
|  | Enhance use of MOUs and Mutual Aid agreements among ESF-1 partners, especially where needed to facilitate resource sharing across state lines | Oct 2013-Sept 2015 | RESF 1

## ESF 2
Goal | Objectives | RESF 2 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Participate in development of NCR Strategic Plan for Voice. | Oct. 2013 - Sept 2015 | ESF 2- CIOs Committee
|  | Investigate feasibility for potential to use NCR ICI for voice communication resiliency | Oct. 2013 - Sept 2015 | ESF 2- CIOs Committee
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | NCR ICI Sustainment Plan and Cost Model | Oct. 2013 - Sept 2015 | ESF 2/CIOs
|  | Expand participation in NCRNet: applications and sites | Oct. 2013 - Sept 2015 | CIOs w/ ESFs & RWGs
|  | Enhance NCRNet Security & review standards & policies | Oct. 2013 - Sept 2015 | CISSO sub-committee
|  | Maintain and expand GIS capabilities | Oct. 2013 - Sept 2015 | GIS Sub-Committee
| Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Assess video sharing expansion across NCRNet | Oct. 2013 - Sept 2015 | ESF 2- CIOs w/subgrantees
|  | Support video sharing through mobile applications | Oct. 2013 - Sept 2015 | ESF 2- CIOs w/subgrantees
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Foster coordination, support maintenance and development of information sharing capabilities. | Oct. 2013 - Sept 2015 | ESF 2/CIOs, ESF 4 & 13
|  | Develop a plan for shared critical services as CAD, RMS & others to support ECC, PSAP & EOC operations | Oct. 2013 - Sept 2015 | ESF 2/CIOs, ESF 4 & 13
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Assist Public Information Officers and Emergency Managers in maintenance and development of new communications tools | Oct. 2013 - Sept 2015 | ESF2/CIOs, ESF 5, & ESF15/PIOs
| Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner. | Review information sharing, data exchange and security methods adopted in NCR for currency and consistency | Oct. 2013 - Sept 2015 | ESF 2 and core ESFs
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Advise on 9-1-1 Interoperability opportunities. | Oct. 2013 - Sept 2015 | ESF 2
|  | Assist in developing strategy for strengthening 911 technical interoperable capabilities | Oct. 2013 - Sept 2015 | ESF 2
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Develop plan for a collaborative information sharing clearinghouse with utility and telecommunications providers to strengthen regional situational awareness | Oct. 2013 - Sept 2015 | ESF 2 and CIP RWG
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Participate in planning for loss of communications infrastructure | Oct. 2013 - Sept 2015 | ESF 2 and CIP RWG
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | Participate in planning for loss of communications infrastructure | Oct. 2013 - Sept 2015 | ESF 2 and CIP RWG
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Participate in Communications Interoperability Courses, Utilities Failure Exercise, Cyber Con Ops Seminar | Oct. 2013 - Sept 2015 | ESF 2, ESF 5 & ETOP
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | Conduct assessment of ICI and IAMs security capabilities & develop long tern 'living' plan to for investments to keep capabilities current | Oct. 2013 - Sept 2015 | ESF2/CIOs & CIP RWG
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues related to interoperable communications; update ICI polices and governance model | Oct. 2013 - Sept 2015 | ESF 2, partners, & MWGOG

## ESF 3A
Goal | Objectives | RESF 3A Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis.
Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis.
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness.
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Work with PIOs on messaging to the public, test in Utilities Failure exercise | Jul-Sep 2014 | PIOs/CIP RPWG/RESF-3A
Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Supply Chain Exercise | Oct 2013-Sept 2015 | CIP RPWG/RESF-3A
|  | Utilities Failure Exercise | Jul-Sep 2014 | ETOP/CIP/RESF-3A/Subgrantee
|  | Response and Coordination to a Prolonged Energy Emergency Tabletop Exercise | Jul-Sep 2014 | ETOP/CIP/RESF-3A/Subgrantee
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Partner with DHS to apply for/conduct a Regional Resilience Assessment (RRAP) of the NCR's water and wastewater systems. | Oct 2013-Sept 2015 | RESF-3A
|  | Partner with the U.S. Army 249th Prime Power Engineer Battalion to carry out electrical assessments of critical water facilities within the NCR. Under the initial proposal, the 249th would assess two facilities each month beginning in JAN 2014, and continuing for several months. | Jan 2014 - Sept 2015 | RESF-3A/U.S. Army
|  | Develop water outage regional plan in coordination with Emergency Managers | Oct 2013-Sept 2015 | CIP RPWG/ RESF 5/ RESF-3A/Planners
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | Maintain Water Security Monitoring capability, ensure a smooth transition to local funding. | Oct 2013-May 2014 | CIP RPWG/RESF-3A
|  | Foster participation in Utilities Failure exercise | Jul-Sep 2014 | ETOP/CIP/RESF-3A/Subgrantee
|  | Maintain WARN website | Oct 2013-Sept 2015 | CIP RPWG/RESF-3A
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events.
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities.

## ESF 3B
Goal | Objectives | ESF 3B Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Participate in development of NCR Strategic Plan for Voice. | on-going | ESF 3B
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | RESF3 Debris: Update RICCS communication list. | Review in December 2013 | John Snarr, COG
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Ensure information is shared with appropriate officials | on-going | ESF 3B
|  | Maintain water security monitoring capability | on-going | ESF 3B
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Develop and ensure communications protocols with PIOs to ensure public is informed of water security actions | on-going | ESF 3B
Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | RESF3 Debris: Renew effort to get any missing jurisdictions to sign the Debris Mutual Aid Operational Plan. Update any information that may have changed for existing signatories. | Get signatures for missing jurisdictions by June 2014 | John Snarr, COG
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure.
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Participate in Radiation Monitoring training | on-going | ESF 3B
|  | Participate in Public Communications training | on-going | ESF 3B
|  | Participate in Utilities Failure exercise | on-going | ESF 3B
|  | Participate in PPE training | on-going | ESF 3B
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues | on-going | ESF 3B

## ESF 4 9 10
Goal | Objectives | RESF 4, 9, 10 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Maintain Radio Cache capability | Oct 2013-Sept 2015 | Radio Managers, ESF4
|  | Participate in development of NCR Strategic Plan for Voice, to include encryption and Interoperability. | Oct 2013-Sept 2015 | ESF 4
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Create regional NCR GIS capability by ensuring local GIS systems are interoperable to foster sharing of operational information | Oct 2013-Sept 2015 | ESF 4, ESF 2
|  | Maintain and expand CAD-to-CAD capabilities, including regional implementation plan, MOUs, and Concept of Operations Plan | Oct 2013-Sept 2015 | ESF 4, subgrantee
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness.
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Continue to work in an inclusive fashion with PIOs, Emergency Managers, and others on regional messaging to the public. | Oct 2013-Sept 2015 | ESF 4, 5, 15
| Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner. | Work with Fusion Centers to develop discipline-specific products | Oct 2013-Sept 2015 | ESF 4, Fusion Centers
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Maintain and expand CAD-to-CAD capabilities , including regional implementation plan, MOUs, and Concept of Operations Plans | Oct 2013-Sept 2015 | ESF 4, ESF 2
|  | Create regional NCR GIS capability by ensuring local GIS systems are interoperable to foster sharing of operational information | Oct 2013-Sept 2015 | ESF 4, ESF 2
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors.
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Develop NCR Regional Continuity of Operations plan for 911 Centers to reduce the likelihood of 911 outages | Oct 2013-Sept 2015 | ESF 4, PSAP Directors, Emergency managers
Develop regional fire suppression plan during water outages
|  | Develop regional fire suppression plan during power outages | Oct 2013-Sept 2015 | ESF 4
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.
| Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | In coordination with NCR NIMS Officers support ICS training for partners like Schools and Public Health | Oct 2013-Sept 2015 | ESF 4, NIMS Officers
|  | Encourage hospitals to participate in relevant exercises | Oct 2013-Sept 2015 | ESF 4
|  | Encourage 911 Centers to participate in relevant exercises | Oct 2013-Sept 2015 | ESF 4, PSAP Directors, Emergency managers
|  | Along with other Public Safety agencies, participate in Active Shooter and IED training and exercises | Oct 2013-Sept 2015 | ESF 4, ETOP
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. |  | Foster participation in Swift Water training | Apr-Jun 2014; Jul- Sep 2014 | ESF 4, ETOP
|  | Foster participation in Water Operations training | Oct 2013-Sept 2015 | ESF 4, ETOP
|  | Foster participation in Mass Casualty Incident Cache exercise | Oct 2013-Sept 2015 | ESF 4, ETOP
|  | Foster participation in Radiation Monitoring training | Oct 2013-Sept 2015 | ESF 4, ETOP
|  | Foster participation in Weapons of Mass Destruction training | Oct 2013-Sept 2015 | ESF 4, ETOP
|  | Foster participation in PPE training | Oct 2013-Sept 2015 | ESF 4, ETOP
|  | Foster participation in IMT training, exercises, and operations | Oct 2013-Sept 2015 | ESF 4, ETOP
|  | Foster participation in Mass Care and Evacuation exercises | Oct 2013-Sept 2015 | ESF 4, ETOP
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | In coordination with Police Chiefs, develop regional on-scene victim care capabilities for Police and Fire personnel in response to an Active Shooter event | Oct 2013-Sept 2015 | ESF 4, 13
|  | In coordination with Police Chiefs, sustain Bomb Squad capabilities | Oct 2013-Sept 2015 | ESF 4, 13
|  | Develop and maintain Swift Water Operations capabilities | Oct 2013-Sept 2015 | ESF 4
|  | Develop local sustainment model for PPE capability | Oct 2013-Sept 2015 | ESF 4
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | In coordination with Emergency managers and Volunteer Coordinators, foster sustainment of CERT programs in the NCR | Oct 2013-Sept 2015 | ESF 4, 5, 16
|  | Continue to work in an inclusive fashion with PIOs, Emergency Managers, and others on regional messaging to the public. | Oct 2013-Sept 2015 | ESF 4, 5,15
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | Encourage hospitals to participate in relevant exercises | Oct 2013-Sept 2015 | ESF 4, ETOP
|  | Fully implement and sustain the NCR Patient Tracking capability | Oct 2013-Sept 2015 | ESF 4, ERS
|  | Work with HM RPWG to maintain and enhance NCR Mass Casualty Care Cache | Oct 2013-Sept 2015 | ESF 4, HM RPWG
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Work with COG Attorney's Committee, and other relevant parties, to resolve IMT deployment issues. Develop local sustainment model for IMT, including succession model | Oct 2013-Sept 2015 | ESF 4, 5
|  | Create regional NCR GIS capability by ensuring local GIS systems are interoperable to foster sharing of operational information | Oct 2013-Sept 2015 | ESF 4, 2
|  | Participate in annual Fire/Police/Emergency Management meeting | Oct 2013-Sept 2015 | ESF 4, 5, 13
|  | Resolve issues with regional implementation of Patient Tracking capability | Oct 2013-Sept 2015 | ESF 4, ERS
|  | Maintain and expand CAD-to-CAD capabilities, including regional implantation plan, MOUs, and Concept of Operations Plans | Oct 2013-Sept 2015 | ESF 4
|  | Assess potential benefits of regional purchasing and procurement programs. | Oct 2013-Sept 2015 | ESF 4, MWCOG
|  | Identify and work to resolve regional policy, procedural, and legal issues | Oct 2013-Sept 2015 | ESF 4

## ESF 5
Goal | Objectives | RESF 5 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Foster participation in biannual communications exercises that test all regional communications platforms. | Sept 2013-Sept 2015 | ESF 5
|  | Maintain WAWAS system capability | Sept 2013-Sept 2015 | ESF 5
|  | Participate in development of NCR Strategic Plan for Voice, to include encryption and Interoperability. | Sept 2013-Sept 2015 | ESF 5
|  | Maintain two-way satellite radio system capability | Sept 2013-Sept 2015 | ESF 5
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Maintain EMNet system capability | Sept 2013-Sept 2015 | ESF 5
| Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Participate in expansion of DOT CCTV project | Sept 2013-Sept 2015 | ESF 5/ESF 1
|  | Participate in Mobile CCTV project | Sept 2013-Sept 2015 | ESF 5
|  | In coordination with CIOs, investigate alternate methods of maintaining VTC regional capability at lower cost | Sept 2013-Sept 2015 | CIOs/ESF 5
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Maintain WebEOC capability, enhance to address emerging technology and lessons learned | Sept 2013-Sept 2015 | ESF 5
|  | Develop Situational Awareness Dashboard capability for all jurisdictions | Sept 2013-Sept 2015 | ESF 5/DCSHEMA
|  | Work to consolidate efforts on regional situational awareness projects. | Sept 2013-Sept 2015 | ESF 5
|  | In coordination with CIOs, investigate alternate methods of maintaining VTC regional capability at lower cost | Sept 2013-Sept 2015 | CIOs/ESF 5
|  | Develop program to share best practices among Emergency Managers and partners | Sept 2013-Sept 2015 | ESF 5
|  | Maintain PROTECT system capability, transition to alternate funding source | Sept 2013-Sept 2015 | ESF 5/METRO
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Complete RFP process for Text Alert capability | 2014 | ESF 5/ Fairfax OEM
|  | In coordination with PIOs, continue to develop regional messages to the public | Sept 2013-Sept 2015 | ESF 5, PIOs
|  | Support PIOs in regional communications efforts to include CapitAlerts and social media | Sept 2013-Sept 2015 | ESF 5, PIOs
|  | In coordination with ESF 6/11 and PIOs, continue to develop coordinated 211 capabilities in the NCR | Sept 2013-Sept 2015 | ESF 5, ESF 6/11, PIOs
| Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner. | Work with Fusion Centers to develop products for Emergency Managers that include actionable intelligence for Emergency Management | Sept 2013-Sept 2015 | ESF 5
|  | Develop and maintain quarterly Fusion Center briefings to ESF 5 meetings | Sept 2013-Sept 2015 | ESF 5
|  | Coordinate with Fusion Centers to ensure Emergency Managers are recipients of all desired/relevant products | Sept 2013-Sept 2015 | ESF 5
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Foster 911 agency participation in training and exercises | Sept 2013-Sept 2015 | ESF 5
|  | Coordinate with 911 Centers to plan to prevent and respond to 911 outages | Sept 2013-Sept 2015 | ESF 5
|  | Foster participation in ICS specific training | Sept 2013-Sept 2015 | ESF 5
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | In coordination with CIP, develop and participate in ELO program for EOCs | Sept 2013-Sept 2015 | ESF 5/CIP
|  | In coordination with CIP, develop regional priority facility restoration list for utilities | Sept 2013-Sept 2015 | ESF 5/CIP
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Develop strategic guidance for Emergency Managers on CIKR | 2013-12-01 | Emergency Planners
|  | Work with CIP RPWG to prioritize planning efforts | Sept 2013-Sept 2015 | ESF 5/CIP
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | Develop and implement projects for shelter resiliency in coordination with CIP | Sept 2013-Sept 2015 | ESF 5/CIP
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Coordinate NCR Emergency Planning | Sept 2013-Sept 2015 | ESF 5
|  | Coordinate planning with NCR ERS programs | Sept 2013-Sept 2015 | ESF 5/ERS
|  | Coordinate NCR NIMS Officers | Sept 2013-Sept 2015 | ESF 5/ETOP
|  | Coordinate NCR Training and Exercise Officers | Sept 2013-Sept 2015 | ESF 5/ETOP
|  | Foster participation in ETOP trainings and exercises | Sept 2013-Sept 2015 | ESF 5/ETOP
|  | Participate in development of annual NCR THIRA | Sept 2013-Sept 2015 | Emergency Planners
|  | Foster participation in Position-specific ICS training | Sept 2013-Sept 2015 | ESF 5/ETOP
|  | Develop regional Sheltering Annex | Sept 2013-Sept 2015 | Emergency Planners
|  | Develop Long-term Recovery Annex model for localities | Sept 2013-Sept 2015 | Emergency Planners
|  | Update COG regional snow response plan with recommendations for addressing gaps. | Sept 2013-Sept 2015 | Emergency Planners
|  | Develop Transportation Evacuation Annex | Sept 2013-Sept 2015 | Emergency Planners
|  | Develop School Preparedness guidance and Seminars on planning for incidents that involve natural hazards, active shooter, school violence, and behavioral health issues | Sept 2013-Sept 2015 | Emergency Planners
|  | Develop Critical Infrastructure/Key Resource Restoration Concept of Operations | Sept 2013-Sept 2015 | Emergency Planners/ CIP RPWG
|  | Develop Cyber Preparedness Plan including COOP model | Sept 2013-Sept 2015 | Emergency Planners
|  | Develop Special Events and Mass Gatherings Model | Sept 2013-Sept 2015 | Emergency Planners
|  | Revise RECP | Sept 2013-Sept 2015 | ESF 5/Planners
|  | Foster staff participation in IMT training, exercises, and operations | Sept 2013-Sept 2015 | ESF 5
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | Foster awareness of efforts of other ESFs | Sept 2013-Sept 2015 | ESF 5
|  | Sustain resource typing efforts, enhance in response to emerging capabilities, in coordination with NIMS Officers | Sept 2013-Sept 2015 | ESF 5/ NIMS Officers
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | Work with Volunteer Coordinators to support NCR Volunteer Development and Coordination | Sept 2013-Sept 2015 | ESF 5/ ESF 16
|  | In coordination with NIMS Officers, work with VOADs to create regional database for resource typing of VOAD assets | Sept 2013-Sept 2015 | ESF 5/NIMS Officers
|  | In coordination with Volunteer Coordinators, support regional Citizen Corps initiatives | Sept 2013-Sept 2015 | ESF 5/ ESF 16
|  | Develop Federal workforce emergency evacuation awareness training and exercise | Sept 2013-Sept 2015 | ESF 5/DCHSEMA
|  | In coordination with PIOs and Volunteer Coordinators, continue regional Community Preparedness and Participation activities | Sept 2013-Sept 2015 | ESF 5/ ESF 16
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | Foster Healthcare participation in training and exercises related to ICS, evacuation, sheltering | Sept 2013-Sept 2015 | ESF 5
|  | Develop regional program to review emergency plans of care facilities | Sept 2013-Sept 2015 | ESF 5
|  | Participate in Patient tracking project to ensure the capability is used for Family Reunification | Sept 2013-Sept 2015 | ESF 5
| Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region. | Develop Federal workforce emergency evacuation awareness training and exercise | Sept 2013-Sept 2015 | ESF 5/DCHSEMA
|  | Foster Mass Care participation in training and exercises related to ICS, evacuation, sheltering | Sept 2013-Sept 2015 | ESF 5
|  | Link local and subregional evacuation plans to coordinate evacuation plans | Sept 2013-Sept 2015 | ESF 5
|  | Identify regional shelters | Sept 2013-Sept 2015 | ESF 5
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Revise RECP | Sept 2013-Sept 2015 | ESF 5/Planners
|  | Revise Ist Hour Checklist | Sept 2013-Sept 2015 | ESF 5/Planners
|  | Develop Mutual Aid Operations Plan | Sept 2013-Sept 2015 | ESF 5/Planners
|  | In coordination with COG Attorney Committee, and other relevant parties, to resolve IMT deployment issues. Develop local sustainment model for IMT, including succession model | Sept 2013-Sept 2015 | ESF 5
|  | Participate in annual Fire/Police/Emergency Management meeting | Sept 2013-Sept 2015 | ESF 5/ ESF4/ ESF 13
|  | Identify and work to resolve regional policy, procedural, and legal issues | Sept 2013-Sept 2015 | ESF 5

## ESF 6 11
Goal | Objectives | ESF 6, 11 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | In collaboration with ESF-2 and RESF-5 ensure that RESF-6/11 agencies are able to communicate by voice to meet operational needs. | Ongoing | ESF 6/11, ESF 2, ESF 5
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | In collaboration with ESF-2 and RESF-5 ensure that RESF-6/11 agencies are able to share data regionally to meet operational needs. | Ongoing | ESF 6/11, ESF 2, ESF 5
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | In collaboration with RESF-2 and RESF-5 ensure that RESF-6/11 agencies are able to participate in and share information via the situational awareness tools deployed throughout the NCR. | Ongoing | ESF 6/11, ESF 2, ESF 5
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | In coordination with Emergency Managers and PIOs, continue to develop coordinated 211 capabilities in the NCR | Ongoing | ESF 6/11, ESF 15, ESF 5
|  | Maintain NCR access to 2-1-1 call centers 24 hours a day, 7 days a week; In Coordination with 2-1-1 NCR Work Group, redesign and improved public search of 2-1-1 metrodc website underway | 2013-2014 | 2-1-1 VA, 2-2-1 MD & 211/311 in DC
|  | In Coordination with 2-1-1 NCR Work Group, maintain updates to the 2-1-1 regional database and improved public search | Ongoing | 2-1-1 VA, 2-2-1 MD & 211/311 in DC
|  | Seek funding to maintain software platform that connects 2-1-1 regional database across state borders and emergency texting. | Spring 2014 | United Way NCA
|  | Maintain NCR access to 2-1-1 call centers 24 hours a day, seven days a week. | Ongoing | 2-1-1 VA, 2-2-1 MD & 211/311 in DC
|  | In coordination with 2-1-1 NCR Work Group, develop back-up plans and agreements and coordinated protocol for preparing for and responding during emergency situations | 2014/2015 | 2-1-1 VA, 2-2-1 MD & 211/311 in DC
|  | In coordination with PIOs and Emergency Managers, continue to develop regional messages to the public. | Ongoing | ESF 6/11, ESF 15, ESF 5
Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Continue to provide support to Shelter Power Task Force in their effort to evaluate back-up power for shelter sites in the NCR. | Ongoing | American Red Cross in the National Capital Region
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure.
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Foster participation in Community Mass Care Management Course | Ongoing effort | ESF 6&11/ETOP
|  | Foster participation in Mass Care and Evacuation exercises | Ongoing effort | ESF 6&11/ETOP
|  | Foster participation in Mass Care and Emergency Assistance Principles course | Ongoing effort | ESF 6&11/ETOP
|  | Offer Coordinated Assistance Network (CAN) Training to NGO's participating in post-disaster client services, case management and recovery assistance. | Ongoing effort | American Red Cross in the National Capital Region
|  | Offer Shelter Fundamentals, Shelter Management and Serving People with Functional and Access needs in Shelters training to government, NGO and private sector partners throughout the NCR | Ongoing effort | American Red Cross in the National Capital Region
|  | Develop and submit PMP for region wide tabletop exercise focused on the transition from response to recovery and initial disaster recovery efforts including case management | By February 28, 2014 | American Red Cross in the National Capital Region
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | In collaboration with ESF-16 ensure that plans and resources are in place to provide opportunities for event-based volunteers and for responding organizations to access event based volunteers in times of disaster | Ongoing | American Red Cross in the National Capital Region
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | Work with EMS providers to maintain and enhance NCR Mass Casualty Care Cache; Family Reunification | Ongoing effort | ESF 8, FIRE/EMS, 6&11
| Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region. | Maintain NCR Mass Care Cache | Ongoing effort | American Red Cross in the National Capital Region
|  | Collaborate with corrections regarding their intrest in supporting mass care feeding operations | By February 28, 2014 | American Red Cross in the National Capital Region
|  | Convene a cross-sector workshop of key stakeholders around post-disaster human services, housing and recovery issues engaging a larger network of partners in the discussion and producing a SWOT analysis as a guide to future efforts | Completed by 6/30/2014 | RESF-6/11, ARC-NCR
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues | Ongoing | ESF 6/11
|  | Working with RESF-5 and CAO/SPG establish the framework, including appropriate MOUs and SOPs through which resources within the NCR Mass Care Cache could potentially be made available for use in jurisdictions outside the NCR | Completed by 6/30/2014 | American Red Cross in the National Capital Region

## ESF 8 HM
Goal | Objectives | HMWG / ERS Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Conduct training to improve ability of all partners to access and use voice communications systems effectively - focus on health care facility partners and communications operators across the NCR. | Present to Oct 2015 | MD ERS Lead with support from NCR ERS
|  | Enhance 800 MHz radio interoperability between public health departments and other healthcare partners, such as hospitals, skilled nursing, fire/ems and others | Present to May 2014 | HMRPWG / NVHA
|  | Install Redundant Communications EMS Telephone System to critical statewide EMS partners in Maryland. | Present to May 2014 | HMRPWG / MIEMSS
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Conduct training to improve ability of all partners to access and use data communications systems effectively - focus on health care facility partners. | Present to May 2015 | NCR ERS programs
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness.
Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions.
| Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner. | Foster Fusion Center information sharing with all disciplines, continue briefings at monthly meetings | Present to Sept 2015 | HMRPWG & NCR ERS
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Undertake metro evacuation planning NCR-wide. | Present to Sept 2015 | DC ERS Lead
|  | Maintain relationships and collaboration with Health Care Systems | Present to Sept 2015 | HMRPWG / NCR ERS Programs
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure.
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Coordinate ERS planning with Emergency Managers and Planners | Present to Sept 2015 | NCR ERS programs
|  | Foster participation in Mass Fatalities Incident Response course, Medical Surge, Mass Care and Evacuation exercises, Medical facilities Evacuation exercise | Present to Sept 2015 | NCR ERS programs
|  | Support ERS steering committees, project management, and coordination on sub-regional and NCR level to achieve multi-disciplinary & multi-jurisdiction coordination with a focus on catastrophic incident priorities. | Present to Sept 2015 | NCR ERS programs
|  | Integrate current MMRS/ERS plans into existing and future jurisdictional and agency plans and SOPs to ensure a seamless response and alignment with Federal (DHS/CDC/ASPR) core capabilities. | Present to Sept 2015 | NCR ERS programs with DC ERS Lead
|  | Maintain effort on updating and alignment of regional operational manuals for Fire/EMS | Present to Sept 2015 | NVERS
|  | Sustain capability to ensure public health and EMS plans are operational and cross-walked across jurisdictions with relevant partners. | Present to Sept 2015 | HMRPWG & NCR ERS
|  | Develop NCR public health and EMS operational plans to address identified gaps from 2010 ESF8 gap analysis. | Present to May 2014 | HMRPWG / Subgrantees
|  | Conduct cross-disciplinary/cross-jurisdictional T&E focused on medical surge for catastrophic events. | Present to Sept 2015 | NCR ERS Programs
|  | Coordinate across NCR sub-regions TEP development and delivery of training (including distance learning) in the area of large-scale or regional incidents. | Present to Sept 2015 | NCR ERS Chair
|  | Coordinate across ERS sub-regions in exercise planning, implementation, and follow-up to include sharing AARs, best practices, and lessons learned focused on regional coordination and preparation for mass casualty incidents. | Present to Sept 2015 | NCR ERS programs
|  | Conduct regional exercise series in 2013 focusing on forward movement of patients / patient tracking capability | Present to May 2014 | MD ERS Lead with support from NCR ERS
|  | Conduct a series of activities that include ambulance strike team training, active shooter response; situational awareness and patient tracking workshop; haz mats mass decon Drill, Chempack training and moulage workshop. Full scale regional exercise with 600-800 patients at two sites to evaluate patient tracking and communications, surge response, forward movement of patients. | Present to May 2014 | MD ERS Lead with support from NCR ERS
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | Complete capability for Tactical emergency casualty care for law enforcement and fire/rescue (kits, education, operationalization). | Present to Sept 2015 | HMRPWG / NCR ERS Programs
|  | Maintain patient tracking capability (finalization of hardware procurement, software integration, integration of systems, training). | Present to Sept 2015 | HMRPWG / Subgrantees
|  | Ensure regional information sharing, awareness, and inventory of resource availability across the sub-regions. Coordinate and integrate inventory management information across sub-regions (regional logistics). | Present to Sept 2015 | HMRPWG / NVERS Lead with support from NCR ERS
|  | Maintain and enhance biosurveillance, detection and reporting capabilities across the NCR | Present to Sept 2015 | HMRPWG
|  | Ensure adequate chemical agent detection for Fire/EMS personnel | Present to Sept 2015 | MD ERS Lead with support from NCR ERS
|  | Ensure ALS units have necessary antidote supplies for surge on annual basis. | Present to Sept 2015 | MD ERS Lead with support from NCR ERS
|  | Support ERS steering committees, project management, and coordination on sub-regional and NCR level to achieve multi-disciplinary & multi-jurisdiction coordination with a focus on catastrophic incident priorities. | Present to Sept 2015 | NCR ERS programs
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | In partnership with NCR volunteer coordinators, sustain capability for Medical Surge Support via Medical Reserve Corps | Present to Sept 2015 | HMRPWG / NCR ERS / Subgrantees
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | Maintain education and outreach with area health care facilities for surge | Present to Sept 2015 | HMRPWG
|  | Sustain regional working groups that plan and manage pharmaceutical and medical supply caches, including storage of same | Present to Sept 2015 | NCR ERS programs
|  | Share pharmaceutical and medical supply information across NCR sub-regions. | Present to Sept 2015 | HMRPWG / NCR ERS programs
|  | Develop NCR Behavioral Health Plan and Operationalize it across NCR. Complete planning with mental health associations to expand behavioral health support in disasters | Present to Sept 2015?? | HMRPWG / MD ERS Lead with support from NCR ERS
|  | Planning with Mental Health Associations to expand behavioral health support in disasters | Present to Sept 2014?? | HMRPWG / MD ERS Lead with support from NCR ERS
|  | Sustain planning, medical supply, and equipment efforts to maintain CI of hospitals and critical health care facilities, such as extended care power planning, surge planning, evacuation planning. | Present to Sept 2015 | HMRPWG / Subgrantees
|  | Sustain and enhance EMS mass casualty equipment and supply caches and assets. | Present to Sept 2015 | HMRPWG / Subgrantees
|  | Support equipment procurement for mass fatality planning and response capability | Present to Sept 2015 | HMRPWG / NCR ERS programs
|  | Continue to develop and maintain patient tracking capability across NCR: Final procurement and distribution of Patient Tracking System equipment for use across the NCR, integrate software and devices into operations, conduct training for all PTS users | Present to Sept 2015 | HMRPWG / NCR ERS programs
| Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region. | Maintain evacuation capability for surge events via evacuation equipment and education. | Present to Sept 2015 | HMRPWG / Subgrantees
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Discuss transition of guidance of ERS to NCR EM committee or joint EM / HMRPWG guidance at NCR level. | Present to May 2014? | HMRPWG / NCR ERS programs
|  | Identify and work to resolve regional policy, procedural, and legal issues such as: mass fatality planning policy across sub-regions. | Present to Sept 2015 | HMRPWG / NCR ERS programs

## ESF 12
Goal | Objectives | RESF 12 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis.
Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis.
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness.
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Work with PIOs on messaging to the public, test in Utilities Failure exercise | Jul-Sep 2014 | PIOs/CIP RPWG/RESF-12/RESF-3A
Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Supply Chain Exercise | Oct 2013-Sept 2015 | CIP RPWG/RESF-12
|  | Utilities Failure Exercise | Jul-Sep 2014 | ETOP/CIP/RESF-12/RESF-3A/Subgrantee
|  | Response and Coordination to a Prolonged Energy Emergency Tabletop Exercise | Jul-Sep 2014 | ETOP/CIP/RESF-12/Subgrantee
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Undertake "Regional Energy Assurance Planning" (EAP) that will (1) Identify, assess and prioritize critical infrastructure (CI) energy requirements; and (2) Evaluate alternative options for "hardening" Critical Infrastructure. | Oct 2013-Sept 2015 | RESF-12
|  | Work with stakeholders in the region to identify three (3) sites in the National Capital Region (NCR) where there is interest and need for deployment of advanced microgrid technology to support power needs for critical infrastructure, and where implementation is feasible from an engineering and technical standpoint. | Oct 2013-Sept 2015 | RESF-12
|  | Participate in FY12 UASI cybersecurity regional planning project | Oct 2013-May 2014 | CIP RPWG/ Arlington County/RESF-12
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | Foster participation in Utilities Failure exercise | Jul-Sep 2014 | ETOP/CIP/RESF-12/Subgrantee
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events.
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities.
Note on E6: Steven Bieber:

## ESF 13
Goal | Objectives | ESF 13 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Participate in development of NCR Strategic Plan for Voice. | October 2013 - September 2015 | RESF 13 + Corrections
|  | Ensure that all three respective 2015 Statewide Communications Interoperability Plans (SCIP) are reviewed for commonalities relevant to the NCR. | March 2015 or 30 days after final SCIP is published | Joint Sub-Committee out of Police and Fire Chiefs
|  | Implement model policy for encryption for Law Enforcement agencies (at least for those pursuing encryption). | October 2013 - September 2015 | RESF 13
|  | Continue to support the establishment and maintenance of radio/voice interoperability within the region and amongst partners. | October 2013 - September 2015 | RESF 13
|  | Support and participate in Voice Communications training and exercises, especially with regard to interoperability | October 2013 - September 2015 | RESF 13
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Evaluate technical solutions that will permit sharing real time video and data on a day to day basis (e.g. Regional Wireless Broadband). | October 2013 - June 2015 | RESF 13 and RESF 4/9/10
|  | Ensure that all three respective 2015 Statewide Communications Interoperability Plans (SCIP) are reviewed for commonalities relevant to the NCR. | March 2015 or 30 days after final SCIP is published | Joint Sub-Committee out of Police and Fire Chiefs
|  | Ensure the sharing and interoperability of CAD data between law enforcement agencies for situational awareness. | October 2013 - September 2015 | RESF 13
|  | Ensure NCR partners are participating in ongoing consultation with their State representatives on the FirstNet State and Local Implementation Grant (SLIGP). | October 2013 - September 2015 | RESF 13
|  | Identify and Implement standard booking data elements to support Corrections and Law Enforcement intelligence efforts. | October 2013 - September 2015 | Corrections Chiefs + RESF 13
| Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Develop Video Sharing to Mobile 1st Responders capabilities | October 2013 - September 2015 | MSP
|  | Identify network requirements for sharing video and what updates may be required to regional infrastructure to allow for such sharing. | October 2013 - September 2015 | RESF 13
|  | Through contact with other major cities, learn best practices on video sharing | October 2013 - September 2015 | RESF 13
|  | Provide training on use of video feeds during an event. | October 2013 - September 2015 | RESF 13
|  | Build on pilot program with GSA for CCTV links to exterior view of federal buildings and investigate availability of networks. | 2015 | MSP and MPD
|  | Collaborate with regional transportation departments on expansion of video sharing project. | October 2013 - September 2015 | RESF 13
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Maintain and expand Corrections Gang/Intelligence Coordination and Cooperation, in partnership with FBI and other Law Enforcement agencies | October 2013 - September 2015 | Corrections Gang/Intel Subcommittee + RESF 13
|  | Continue to expand law enforcement CAD data sharing in the NCR to promote real time situational awareness to the officer level. | October 2013 - September 2015 | RESF 13
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | In coordination with PIOs, evaluate communications tools currently available in the NCR and nationwide and social media tools in an effort to identify a best practice for community notifications. | 2015-03-01 | RESF 13
|  | Coordinate with PIOs on regional messaging. | October 2013 - September 2015 | RESF 13
|  | Ensure that Corrections Officials have access to all relevant public messaging and develop protocols for including their messaging into primary PIO/JIC messaging | October 2013 - September 2015 | Corrections Chiefs
| Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner. | Maintain Fusion Center analysis capabilities. | October 2013 - September 2015 | RESF 13
|  | Foster collaboration between Fusion Centers. | October 2013 - September 2015 | RESF 13
|  | Continue to develop Fusion Center products. | October 2013 - September 2015 | RESF 13
|  | Develop and maintain TAC Intelligence Integration and Analysis Tool. | October 2013 - September 2015 | RESF 13
|  | Sustain AFIS capabilities | October 2013 - September 2015 | RESF 13/Project Manager
|  | Sustain LInX program | October 2013 - September 2015 | RESF 13/Project Manager
|  | Sustain License Plate Reader capability | October 2013 - September 2015 | RESF 13/Project Manager
|  | Evaluate tools such as AWARE, Palenteer and others, for development of a regional analysis capability. | October 2013 - September 2015 | RESF 13
|  | Enable opportunities for Corrections Intel Personnel to support Fusion Center analysis capabilities | October 2013 - September 2015 | Corrections Gang/Intel Subcommittee + RESF 13
|  | Foster collaboration between Corrections Intel Personnel and Fusion Centers | October 2013 - September 2015 | Corrections Chiefs + RESF 13
|  | Continue to develop Corrections supported products | October 2013 - September 2015 | Corrections Chiefs
|  | Facilitate Corrections access and support for TAC Intelligence Integration and Analysis Tool | October 2013 - September 2015 | Corrections Chiefs + RESF 13
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Incorporate 911 agencies in ICS position specific training to foster collaboration and coordination | October 2013 - September 2015 | RESF 13/911 Directors
|  | Collaborate with 911 agencies on scripting messaging for incidents. | October 2013 - September 2015 | RESF 13/ 911 Directors
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Continue to maintain outreach to the public and private sectors by providing ongoing briefings on suspicious activity reporting (SAR) and active shooter preparation response. | October 2013 - September 2015 | MPD/Fusion Centers
|  | Collaborate with critical infrastructure analysts to determine critical sites within the region for potential vulnerability survey. | October 2013 - September 2015 | MPD/Fusion Centers
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Continue to collaborate with Council of Governments and the CIP RPWG | October 2013 - September 2015 | RESF 13 and CIP
|  | Identify if there may be opportunities for Corrections to support or supplement critical infrastructure in the event of a catastrophic disaster | October 2013 - September 2015 | Corrections Chiefs and CIP
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | Continue to work and collaborate with the critical infrastructure analysts and reach out to Public Sector sites. | October 2013 - September 2015 | RESF 13
|  | Foster collaboration between Fusion Centers and CIP RPWG. | October 2013 - September 2015 | RESF 13 and CIP
|  | Review Corrections Resiliency Plans and explore opportunities to increase resiliency in light of Corrections Mutual Aid Operations Plan (MOAP). | October 2013 - September 2015 | Corrections Chiefs and CIP
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Foster staff participation in IMT training, exercises, and operations. | October 2013 - September 2015 | RESF 13
|  | Foster participation in Evacuation and re-entry Planning course. | October 2013 - September 2015 | RESF 13
|  | Foster participation in Radiation Monitoring training. | October 2013 - September 2015 | RESF 13
|  | Foster participation in Weapons of Mass Destruction training, | October 2013 - September 2015 | RESF 13
|  | Foster participation in SWAT/K9 Integration Training. | October 2013 - September 2015 | RESF 13
|  | Foster participation in Multi-jurisdictional/regional bomb/active shooter tabletop exercise. | October 2013 - September 2015 | RESF 13
|  | Foster participation in Explosive Breachers Certification Course. | October 2013 - September 2015 | RESF 13
|  | Foster participation in Regional SWAT training. | October 2013 - September 2015 | RESF 13
|  | Foster participation in ICS training and position specific training. | October 2013 - September 2015 | RESF 13
|  | Foster Corrections staff participation in IMT training, exercises, and operations | October 2013 - September 2015 | Corrections Chiefs + Corrections Trainers
|  | Foster Corrections participation in Evacuation and re-entry Planning course | October 2013 - September 2015 | Corrections Chiefs + Corrections Trainers
|  | Provide Weapons of Mass Destruction training, Radiation Monitoring training and other related training as appropriate for Corrections Personnel | October 2013 - September 2015 | Corrections Chiefs + Corrections Trainers
|  | Develop coordinated training and exercise program across NCR Corrections Institutions | October 2013 - September 2015 | Corrections Chiefs + Corrections Trainers
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | Bomb Squad Sustainment. | October 2013 - September 2015 | RESF 13
|  | Tactical Team Enhancement for Additional Teams. | October 2013 - September 2015 | RESF 13
|  | Procure Long Range Night Vision Sights. | October 2013 - September 2015 | RESF 13
|  | WMD Operations Training - Continuation. | October 2013 - September 2015 | RESF 13
|  | PPE Replacement. | October 2013 - September 2015 | RESF 13
|  | Tactical Operations Respirators/PPE. | October 2013 - September 2015 | RESF 13
|  | Identify recovery requirements and develop plans for regional coordination for recovery operations. | October 2013 - September 2015 | RESF 13
|  | Evaluate the need for an “Active shooter Go Kit” for patrol officers. Develop specific requirements for such a kit, if deemed necessary | October 2013 - September 2015 | RESF 13
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | Offer active shooter preparedness training and information for the community, especially for workplaces, schools, and government partners. | October 2013 - September 2015 | RESF 13
|  | Coordinate and conduct trainings with PIOs and volunteer organizations | October 2013 - September 2015 | RESF 13
|  | Inclusion of active shooter training within key volunteer/ community training programs | October 2013 - September 2015 | RESF 13
|  | Continue to share information regionally on preparedness activities and best practices. | October 2013 - September 2015 | RESF 13
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | Continue to drill and exercise the Strategic National Stockpile (SNS) throughout the NCR. | October 2013 - September 2015 | RESF 13
|  | Expand the use of trauma kits issued to law enforcement personnel to all NCR agencies, conduct training. | October 2013 - September 2015 | RESF 13
| Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region. | Enhance coordination between evacuation plans across NCR. | October 2013 - September 2015 | RESF 13
|  | Continue to coordinate regionally regarding mass evacuation to include traffic and walkout evacuation plans. | October 2013 - September 2015 | RESF 13
|  | Continue to exercise evacuation plans with NCR partners | October 2013 - September 2015 | RESF 13
|  | Review, update, and coordinate mass care shelter security plans. | October 2013 - September 2015 | RESF 13
|  | Coordinate with other appropriate ESFs, including ESFs5,6 & 8, to Review, update, coordinate & exercise family reunification plans | October 2013 - September 2015 | RESF 13
|  | Review and Update Corrections Evacuations Plans in light of Corrections Mutual Aid Operations Plan (MOAP) | October 2013 - September 2015 | Corrections Chiefs
|  | Identify opportunities for Corrections to increase their roles as support agencies for Mass Care | October 2013 - September 2015 | Corrections Chiefs + RESF 6
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues. | October 2013 - September 2015 | RESF 13
|  | Identify and resolve issues hindering CAD data sharing across the region. | October 2013 - September 2015 | RESF 13
|  | Advocate for NCR capability for first responder identification programs (e.g. FRAC). | October 2013 - September 2015 | RESF 13
|  | Ensure AFIS Capabilities are not threatened by policy issues | October 2013 - September 2015 | RESF 13
|  | Ensure License Plate Reader capabilities are not threatened by policy issues | October 2013 - September 2015 | RESF 13
|  | Ensure sharing of video camera feeds are not hindered by policy issues. | October 2013 - September 2015 | RESF 13
|  | Identify and work to resolve regional policy, procedural, and legal issues re: Corrections | October 2013 - September 2015 | Corrections Chiefs
|  | Develop and Implement Corrections Mutual Aid Operations Plan (MOAP) | October 2013 - September 2015 | Corrections Chiefs
|  | Identify and resolve issues around Corrections mutual aid across state lines | October 2013 - September 2015 | Corrections Chiefs

## ESF 15
Goal | Objectives | ESF 15 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis.
Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis.
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness.
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Maintain Virtual Joint Information Center capability | on-going | ESF 15
|  | In coordination with ESF 6/11 and Emergency Managers, continue to develop coordinated 211 capabilities in the NCR | on-going | ESF 15, 6/11, 5
|  | Assist Emergency Managers with messaging to the Public using Text Alert Notification system | on-going | ESF 15, 5
|  | In coordination with ESF 6/11 and Emergency Managers, continue to develop coordinated 211 capabilities in the NCR | on-going | ESF 15, 5, 6/11
Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors.
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure.
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Foster staff participation in IMT training, exercises, and operations | on-going | ESF 15
|  | Ensure participation in Advanced Public Information Officer Course | on-going | ESF 15
|  | Ensure participation in PIO Train-the-Trainer Course | on-going | ESF 15
|  | Ensure participation in Public Information Course | on-going | ESF 15
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | In coordination with Emergency Managers and Volunteer Coordinators, continue Community Preparedness and Participation activities | on-going | ESF 15
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues | on-going | ESF 15

## ESF 16
Goal | Objectives | ESF 16 Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Foster participation of amateur radio (ARES/RACES) in communication exercises | Sept 2013-Sept-2015 | RESF 16
Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis.
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Foster participation of EOC staff in WebEOC training and exercises | Sept 2013-Sept-2015 | RESF 16/RESF 5/Fairfax County OEM
|  | Ensure each Volunteer Coordinator has access to appropriate regional boards in WebEOC | Sept 2013-Sept-2015 | RESF 16/RESF 5/Fairfax County OEM
|  | Ensure Volunteer Coordinators receive training in RICCS usage so they can send messages to ESF 16 groups | Sept 2013-Sept-2015 | RESF 16/COG
|  | Along with CIOs, analyze/undertake creation of a regional virtual system for Donations and Volunteer Management to foster information sharing | Sept 2013-Sept-2015 | RESF 16/CIOs
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | In coordination with Emergency Managers and PIOs, continue to develop regional messages to the public | Sept 2013-Sept-2015 | RESF 16/PIOs/RESF 5
|  | Work with PIOs to develop regional foreign language messages to the public regarding donations and volunteer opportunities | Sept 2013-Sept-2015 | RESF 16/PIOs
Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors.
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure.
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | In coordination with Emergency Managers and NIMS Officers, develop regional standards and ensure EOC staff receives ICS position specific training. | Sept 2013-Sept-2015 | RESF 16
|  | Assist Emergency Managers with updates to Volunteer and Donations Management Annexes to local EOPs | Sept 2013-Sept-2015 | RESF 16
|  | Develop regional program for National Preparedness Month activities | Sept 2013-Sept-2015 | RESF 16
|  | Coordinate volunteer efforts with state and national programs like Preparedness Month and The Great Shake Out. | Sept 2013-Sept-2015 | RESF 16
|  | Develop biannual regional volunteer activation exercise to update volunteer contact information and reaffirm commitment | Sept 2013-Sept-2015 | RESF 16
|  | Foster participation in the Long-term Recovery exercise | Spring 2014 | RESF 16/ETOP
|  | Foster Donations and Volunteer Management participation in regional training and exercises | Sept 2013-Sept-2015 | RESF 16
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | Update regional MOU for sharing of volunteers | Sept 2013-May 2014 | RESF 16
|  | Develop regional strategy for volunteer utilization | Sept 2013-Sept-2015 | RESF 16
|  | Train two million volunteers in preparedness and mitigation activities by May 2014 | Sept 2013-May 2014 | RESF 16
|  | Continue to track number of recruited volunteers and public trained | Sept 2013-Sept-2015 | RESF 16
|  | Coordinate volunteer efforts with state and national programs like Preparedness Month and The Great Shake Out. | Sept 2013-Sept-2015 | RESF 16
|  | Develop biannual regional volunteer activation exercise to update volunteer contact information and reaffirm commitment | Sept 2013-Sept-2015 | RESF 16
|  | Continue NCR Volunteer Development and Coordination along with Emergency Managers | Sept 2013-Sept-2015 | RESF 16
|  | Continue to build relationships with the private sector and non-profits | Sept 2013-Sept-2015 | RESF 16
|  | In coordination with Emergency Managers continue Community Preparedness and Participation activities | Sept 2013-Sept-2015 | RESF 16
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | Continue to support operations with recruitment and placement of volunteers in coordination with RESF 8 | Sept 2013-Sept-2015 | RESF 16
| Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region. | Continue to support operations with recruitment and placement of volunteers in coordination with Emergency Managers and RESF 6 | Sept 2013-Sept-2015 | RESF 16
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Update regional MOU for sharing of volunteers | Sept 2013-May 2014 | RESF 16
|  | Continue to share local best practices for expansion into regional programs | Sept 2013-Sept-2015 | RESF 16
|  | Along with CIOs, analyze/undertake creation of a regional virtual system for Donations and Volunteer Management to foster information sharing | Sept 2013-Sept-2015 | RESF 16
|  | Identify and work to resolve regional policy, procedural, and legal issues | Sept 2013-Sept-2015 | RESF 16

## CIP
Goal | Objectives | CIP Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Foster collaboration with owners/managers to develop resiliency and protection of NCR assets. | Oct 2013-Sept 2015 | CIP RPWG/ESF 2
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Foster collaboration with owners/managers to develop resiliency and protection of NCR assets. | Oct 2013-Sept 2015 | CIP RPWG/ESF 2
| Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Foster collaboration with owners/managers to develop resiliency and protection of NCR assets. | Oct 2013-Sept 2015 | CIP RPWG/ESF 2
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness.
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Work with PIOs on messaging to the public, test in Utilities Failure exercise | Jul-Sep 2014 | PIOs/CIP RPWG
| Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner. | Continue Fusion Center monthly briefings to CIP RPWG | Oct 2013-Sept 2015 | Fusion Centers/ CIP
|  | Hold SAR training for CIKR owners | Oct 2013-Sept 2015 | Fusion Centers/ CIP
|  | Develop/maintain CIKR Intelligence Bulletins | Oct 2013-Sept 2015 | Fusion Centers/ CIP
|  | Foster strong Fusion Center CIKR analysis capabilities in NCR | Oct 2013-Sept 2015 | Fusion Centers/ CIP
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Foster collaboration with owners/managers to develop resiliency and protection of NCR assets. | Oct 2013-Sept 2015 | CIP RPWG
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Define Critical Infrastructure in the NCR | Oct 2013-Dec 2013 | CIP RPWG/ESFs
|  | Determine priority sectors in private, public, and first responder lifeline functions | Oct 2013-Dec 2013 | CIP RPWG
|  | Build on NCR THIRA to prioritize CIP investments in the NCR | Oct 2013-Sept 2015 | CIP RPWG/ESFs
|  | Coordinate with other RESFs, especially RESF 5 and ESF 2 on CIP priorities and projects | Oct 2013-Sept 2015 | CIP RPWG/ESFs
|  | Articulate and promote private sector benefits to participation and collaboration with NCR CIP RPWG | Oct 2013-Sept 2015 | CIP RPWG
|  | Share best practices in CIP to develop regional programs | Oct 2013-Sept 2015 | CIP RPWG
|  | Supply Chain Exercise | Oct 2013-Sept 2015 | CIP RPWG
|  | NCR CI/KR Recovery ConOps Seminar or Workshop | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Cybersecurity Exercise | Fall 2014 | ETOP/CIP/Subgrantee/ESF 2
|  | Utilities Failure Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Response and Coordination to a Prolonged Energy Emergency Tabletop Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Develop and implement relationship building efforts, especially with respect to priority sector identification. | Jul-Aug 2014 | ETOP/CIP/Subgrantee
|  | Develop Regional ELO program for EOCs in priority lifeline functions | Oct 2013-Sept 2015 | CIP RPWG
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Build on NCR THIRA to prioritize CIP investments in the NCR | Oct 2013-Sept 2015 | CIP/EOCs/Private Sector Partners
|  | Share best practices in CIP to develop regional programs | Oct 2013-Sept 2015 | CIP RPWG
|  | Coordinate with other RESFs, especially RESF 5 and ESF 2 on CIP priorities and projects | Oct 2013-Sept 2015 | CIP RPWG/ESFs
|  | Work with Emergency Managers and Emergency Planners to develop program to prioritize and undertake planning efforts within priority sectors | Oct 2013-Sept 2015 | CIP RPWG/ RESF 5/ Planners
|  | Conduct Cybersecurity Exercise | Fall 2014 | ETOP/CIP/Subgrantee
|  | Develop water outage regional plan in coordination with Emergency Managers | Oct 2013-Sept 2015 | CIP RPWG/ RESF 5/ Planners
|  | Participate in FY12 UASI cybersecurity regional planning project | Oct 2013-May 2014 | CIP RPWG/ Arlington County/ESF 2
|  | Implement NCR Critical Infrastructure Database FY12 UASI project | Oct 2013-May 2014 | CIP RPWG/VAHS
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | Build on NCR THIRA to prioritize CIP investments in the NCR | Oct 2013-Sept 2015 | CIP RPWG
|  | Share best practices in CIP to develop regional programs | Oct 2013-Sept 2015 | CIP RPWG
|  | Coordinate with other RESFs, especially RESF5, on priorities and projects | Oct 2013-Sept 2015 | CIP RPWG/ESFs
|  | Maintain Water Security Monitoring capability, ensure a smooth transition to local funding. | Oct 2013-May 2014 | CIP RPWG
|  | Foster participation in Utilities Failure exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Develop and implement cost-effective projects to ensure the protection/resiliency of publically owned critical infrastructure | Oct 2013-Sept 2015 | CIP RPWG
|  | Maintain WARN website | Oct 2013-Sept 2015 | CIP RPWG/COG
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Develop exercise opportunities for private sector partners | Oct 2013-Sept 2015 | CIP RPWG
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | Foster collaboration to develop projects to enhance resiliency of the healthcare system | Oct 2013-Sept 2015 | CIP RPWG
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Ensure NCR CIP efforts are consistent with PPD-21 and revised NIPP | Nov 2013-Sept 2015 | CIP RPWG
|  | Ensure state and local databases are interoperable in order to facilitate information sharing when appropriate | Oct 2013-Sept 2015 | CIP RPWG
|  | Identify and work to resolve regional policy, procedural, and legal issues | Oct 2013-Sept 2015 | CIP RPWG

## ETOP
Goal | Objectives | ETOP Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis.
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | NCR Emergency Evacuation Transportation Seminar/Training | Nov 2013-May 2014 | ETOP/Subgrantee
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | WebEOC Sustainment Training (FCOEM) | Jan-Sep 2014 | Fairfax OEM
|  | Bi-Annual EOC Communications Drill | May-Sep 2014 | Don Willis
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Regional Media Seminar | Jan-Sep 2014 | NCR PIOs
|  | ICS training to enhance understanding of information sharing process, establishing and managing a JIC and promoting the JIS. | Nov 2013 - Dec 2014 | NCR NIMS Officers
Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Bi-Annual EOC Communications Drill | May-Sep 2014 | Don Willis
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Supply Chain Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | NCR CI/KR Recovery ConOps Seminar or Workshop | Fall 2014 | ETOP/CIP/Subgrantee
|  | Cybersecurity Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Utilities Failure | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Response and Coordination to a Prolonged Energy Emergency Tabletop Exercise | Jul-Aug 2014 | ETOP/CIP/Subgrantee
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Response and Coordination to a Prolonged Energy Emergency Tabletop Exercise | Jul-Aug 2014 | ETOP/CIP/Subgrantee
|  | Utilities Failure Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Cybersecurity Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | NCR Senior Leaders Seminar | Sep-Dec 2014 | ETOP/CIP/Subgrantee
|  | NCR CI/KR Recovery ConOps Seminar or Workshop | Fall 2014 | ETOP/CIP/Subgrantee
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Response and Coordination to a Prolonged Energy Emergency Tabletop Exercise | Jul-Aug 2014 | ETOP/CIP/Subgrantee
|  | Utilities Failure Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | Cybersecurity Exercise | Jul-Sep 2014 | ETOP/CIP/Subgrantee
|  | NCR Senior Leaders Seminar | Sep-Dec 2014 | ETOP/CIP/Subgrantee
|  | NCR CI/KR Recovery ConOps Seminar or Workshop | Fall 2014 | ETOP/CIP/Subgrantee
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Maintain TEO coordination through monthly meetings | 2013-Sept 2015 | TEO Officers
|  | Maintain NIMS Officer coordination through monthly meetings | 2013-Sept 2015 | NCR NIMS Officers
|  | Manage TEP priority events to ensure successful outcomes. | 2013-2015 | ETOP
|  | Coordinate with Emergency Managers on cycle of planning, training, and exercises. | 2013-2015 | ETOP
|  | Continue to foster collaboration with partners across the NCR. | May-Sep 2014 | ETOP
|  | Local and Regional Stakeholders Multi-Discipline Exercise | May-Sep 2014 | ETOP/Subgrantee
|  | NCR Special Events Template Seminar or Workshop | Summer 2014 | ETOP/Subgrantee
|  | NCR Long-term Recovery Annex Seminar or Workshop | Spring 2014 | ETOP/Subgrantee
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | Bomb/Active Shooter | Apr-Sep 2014 | ETOP/Subgrantee
|  | Active Shooter Response Exercise | May-Sep 2014 | ETOP/Subgrantee
|  | Three to Four WMATA Multi-Jurisdictional Exercises | Mar-Aug 2014 | ETOP/Subgrantee
|  | Two Swift Water Exercises Involving All Nine Teams | Apr-Jun 2014; Jul- Sep 2014 | ETOP/Subgrantee
|  | Explosive Breachers Certification Course (2013) | 41699 | ETOP/Subgrantee
|  | Chemical Release | Jul-Sep 2014 | ETOP/Subgrantee
|  | Continue robust ICS/EOC training program for the NCR | NOV 2013 - DEC 2014 | NCR NIMS Officers
|  | Three SWAT/K9 integration classes (2013 & 2014 ) | Dec 13, Apr 14, Sep 14 | ETOP/Subgrantee
|  | Capital Shield | Sep 2014 | ETOP/Subgrantee
| Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities. | Incorporate NGOs into ICS/EOC training programs for the NCR | NOV 2013 - DEC 2014 | NCR NIMS Officers
|  | Regional Volunteer Reception Center Exercise | 2014-09-01 | ETOP/Subgrantee
| Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events. | NCR Communications Exercise for Medical Facilities | Mar-May 2014 | ETOP/Subgrantee
|  | Emergency Response System Regional Building Block Functional Exercises (MIEMSS) | Nov 13-May 2014 | ETOP/Subgrantee
|  | Chemical Release | Jul-Sep 2014 | ETOP/Subgrantee
|  | Initial Response Exercise | Apr-Jun 2014 | ETOP/Subgrantee
|  | Incorporate ICS/EOC training programs for the NCR as it relates to Mass Care Management | NOV 2013 - DEC 2014 | NCR NIMS Officers
|  | Active Shooter Response Exercise | May-Sep 2014 | ETOP/Subgrantee
| Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region. | Response and Coordination to a Prolonged Energy Emergency Tabletop Exercise | Jul-Aug 2014 | ETOP/Subgrantee
|  | Chemical Release | Jul-Sep 2014 | ETOP/Subgrantee
|  | Three to Four WMATA Multi-Jurisdictional Exercises | Mar-Aug 2014 | ETOP/Subgrantee
|  | NCR Emergency Evacuation Transportation Seminar/Training | Nov 2013-May 2014 | ETOP/Subgrantee
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | ICS Position-Specific Training for NCR EOCs | Nov 2013 - Jun 2014 | NCR NIMS Officers
|  | ICS EOC management training for the NCR EOCs | NOV 2013 - DEC 2014 | NCR NIMS Officers
|  | Identify and work to resolve regional policy, procedural, and legal issues. | 2013-Sept 2015 | ETOP

## 911
Goal | Objectives | PSAP Directors Tasks and Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Continued collaboration day-to-day on an operational and technical basis between all local, state, regional, federal and private organizations on voice communications | Oct 2013-Sept 2015 | PSAP Directors
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Continued collaboration day-to-day on an operational and technical basis between all local, state, regional, federal and private organizations on data communications | Oct 2013-Sept 2015 | PSAP Directors
| Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Working jointly with local, state, regional, federal and private organizations continue to develop and refine video sharing capabilities | Oct 2013-Sept 2015 | PSAP Directors
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Through the use of all means available, collect, analyze and disseminate information for appropriate officials to keep them informed and aware of day-to-day operations and during crisis situation | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
| Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions. | Develop, refine and employ communications tools to keep the public informed on a day-to-day basis and during a crisis situation to provide information on appropriate actions by the public and officials | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Continue collaboration day-to-day on an operational and technical basis between all local, state, regional, federal and private organizations on 9-1-1 | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors. | Continue collaboration and develop relationships among local, state, regional, federal and private organizations on 9-1-1 infrastructure | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
| Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Continue refinement and of regional plans on continuity of 9-1-1 services and communications with the public in the event of the loss of private or public infrastructure | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
| Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency. | In collaboration and through cooperation with 9-1-1 service providers and vendors develop plans and actions to ensure public sector infrastructure protection and resiliency | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events. | Foster staff participation in ICS specific training | Sept 2013-Sept 2015 | PSAP Directors/ ESF 5/ ETOP
|  | Foster staff participation in training and exercises | Sept 2013-Sept 2015 | PSAP Directors
|  | Coordinate with Emergency Managers/Planners to plan to prevent and respond to 911 outages | Sept 2013-Sept 2015 | PSAP Directors/ ESF 5/ Emergency Planners
|  | In collaboration and through cooperation with 9-1-1 service providers and vendors plan and perform semi-annual 9-1-1 outage drills | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
| Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue. | Encourage localities to work with their State and Federal regulatory authorities and Legislators as needed to ensure, through proper oversight, best practices and procedures for reliability and continuity of 9-1-1 service. | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues | Oct 2013-Sept 2015 | PSAP Directors, PSAP Directors Committee and Chair

## IC
Goal | Objectives | Interoperability Council Tasks/Outcomes | Timeline | Responsible Party
Goal One: Ensure Interoperable Communications: Ensure NCR partners have the ability to transmit and receive voice, data, and video communications. | Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis. | Inventory assessment | 3/2014, then annual updates | SWICs in coordination with ESF 4, 13
|  | Command Vehicle integration | 3/2014, then annual updates | SWICs in coordination with ESF 4, 13
|  | WAWAS and NAWAS | 3/2014, then annual updates | SWICs in coordination with ESF 4, 13
|  | Ensure regular testing of satellite communications capabilities | 3/2014, then annual updates | SWICs in coordination with ESF 4, 13
|  | Provide training and exercises that focus on coordination of multiple agencies sharing of voice communication to include different sectors such as DDOT, DC WATER, DPW communicating with VA FEMS. | 3/2014, then annual updates | SWICs in coordination with ESF 4, 13
|  | Develop interoperability communication coordination/ patches in both the secure and Un-secure mode for cross communication. | 3/2014, then annual updates | SWICs in coordination with ESF 4, 13
|  | Cache deployment | 3/2014, then annual updates | SWICs in coordination with ESF 4, 13
| Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis. | Work with CIO and other variousCOG committee's on future needs and strategic plan | 12/2014, then annual updates | SPOCs, SWICs, CIOs
|  | Coordination with other COG groups to develop plans for information the assessment and gap analysis to establish what can be shared. | 12/2014, then annual updates | SPOCs, SWICs, CIOs
|  | Participate in and Influence FirstNet planning and deployment in the region. | 12/2014, then annual updates | SPOCs, SWICs, CIOs
|  | Strategic plan for region- continue | 12/2014, then annual updates | SPOCs, SWICs, CIOs
| Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Develop a list of which resources can be shared, to include private sector. | 3/2014, then annual updates | SPOCs, SWICs, CIOs
|  | Participate in project for Video Sharing to Mobile 1st Responders. | 3/2014, then annual updates | SWIC- coordination. ESF1, 13
Goal Two: Enhance Information Sharing and Situational Awareness: Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public. | Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Coordinate the devlopment of data sharing requirements and technology requirements | Ongoing | CIO, SWIC- coordination
|  | Integration of technology | Ongoing | CIO, SWIC- coordination
Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions.
Objective 2.3: Increase Fusion Center and NCR public safety partners’ ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
| Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues. | Back up MOU's | Ongoing | IC, 911 Directors
|  | COML integration and ICS | Ongoing | IC, 911 Directors
|  | Technology integration to dispatcher | Ongoing | IC, 911 Directors
|  | Text to voice information | Ongoing | IC, 911 Directors
|  | Patching and coordination of system use by policy development | Ongoing | IC, 911 Directors
Goal Three: Critical Infrastructure Planning and Resiliency: Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR. | Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors.
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure.
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.
Goal Four: Ensure Regional Core Capabilities: Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR. | Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events.
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
| Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Identify and work to resolve regional policy, procedural, and legal issues | on-going | IC