## Slide 1: NCR Homeland Security Strategic Plan
2013 Update Process
Presentation to Emergency Preparedness Council
November 13, 2013

## Slide 2: Presentation Overview
History of the NCR Strategic Plan
Intent of Plan Refresh
Review of the process and Methodology
Revision Highlights: Goals and Objectives
Snapshots from Work Plans
Next Steps

## Slide 3: History/Purpose of Strategic Plan
2005 DHS requirement
  EPC “owns” plan as UASI UAWG
Plan written in 2010
  DHS requirement of 5 year lifecycle
Refresh effort commenced Fall 2012
Guide for improving the preparedness of the Region
Ensures citizen preparedness and protection against all hazards
Requirement for UASI funding
    Is NOT an operational plan

## Slide 4: The Intent of the Plan Refresh
Build on existing Plan
Reflect maturity of effort
Focus on priority Regional activities for next 2 years
Clarify/simplify language
Address GAO findings regarding no metrics in 2010 plan
  Keep Goals and Objectives
  Replace “Initiatives” with Work Plans
Provide solid starting point for new PMO

## Slide 5: Process for 2013 Plan Update
Advisory Board and SPG approval of methodology/product
Advance notice to all RESF/RPWG; July 8
Compile first draft, request comments; July 10
Brief all RESF/RPWG in July
Receive recommended edits by July 24
Develop draft updated Goals and Objectives
Review draft updated Plan with all RESF/RPWGs
  WebExs to validate revisions
Present to EPC September 11th
Develop Work Plan Appendices
Deliver Revised Plan to EPC at November meeting

## Slide 6: Methodology of Plan Refresh
What is important?
  4 Goals: Interoperable Communication
        Info Sharing/Situational Awareness
        Critical Infrastructure Planning and Resiliency
        Regional Core Capabilities
What do we need to do?
  Objectives: programs or groups of projects necessary to accomplish Goals
How will we do it?
  Work Plans: Detailed list of tasks/outcomes necessary for RESF/RPWG to accomplish Objectives

## Slide 7: Goal 1: Ensure Interoperable Communications
Ensure NCR partners have the ability to transmit and receive voice, data, and video communications.
Objective 1.1: By employing a strategic approach, ensure NCR partners can communicate by voice in all environments and on a day-to-day basis.
Objective 1.2: By employing a strategic approach, ensure NCR partners can communicate and share necessary, appropriate data in all environments and on a day-to-day basis.
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners.

## Slide 8: Goal 2: Enhance Information Sharing and Situational Awareness
Ensure NCR partners collect, analyze, and share the information needed to make informed and timely decisions; take appropriate actions; and communicate accurate, timely information with the public.
Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness.
Objective 2.2: Ensure NCR partners employ a variety of communications tools to inform the public and recommend appropriate actions.
Objective 2.3: Increase Fusion Center and NCR public safety partners ability to collaborate, collect, analyze, share, and disseminate intelligence & investigative information in a timely and actionable manner.
Objective 2.4: Continue to develop 911 agency collaboration and coordination on regional issues.

## Slide 9: Goal 3: Enhance Critical Infrastructure Planning and Resiliency
Enhance the protection and resilience of public and private critical infrastructure and plan for loss of critical infrastructure to reduce the impact on the public and state and local governments in the NCR.
Objective 3.1: Build Public/Private sector relationships and collaboration in priority critical infrastructure sectors.
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure.
Objective 3.3: Ensure Public sector critical infrastructure protection and resiliency.

## Slide 10: Goal 4: Ensure Regional Core Capabilities
Develop and maintain regional core capabilities for prevention, preparedness, response, and recovery to threats and hazards that may impact the NCR.
Objective 4.1: Continue to develop and coordinate plans among NCR partners and ensure a region-wide training and exercise program to strengthen prevention, preparedness, response, and recovery efforts from all-hazards events.
Objective 4.2: Ensure the NCR has a region-wide capability to prevent, detect, respond, and recover in a timely manner to attacks and other events requiring tactical response and technical rescue.

## Slide 11: Goal 4 continued
Objective 4.3: Strengthen individual, community, and workplace preparedness for emergency events through volunteer engagement and public participation in preparedness activities.
Objective 4.4: Enhance the NCR’s healthcare system preparedness and response to health and medical consequences of regional events.
Objective 4.5: Improve the NCR’s ability to evacuate and provide mass care for the diverse populations of the region.
Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities.

## Slide 12: Workplans
  Detailed list of tasks/outcomes necessary for RESF/RPWG to accomplish Objectives
Tasks are priorities for the next two (2) years
RESF/RPWGs held work sessions to identify all tasks – Current tasks and new tasks
Workplans will be reviewed during each RESF/RPWG meeting to measure progress

## Slide 13: Snapshot from Work Plan: Goal 1
Objectives | ESF 1 Tasks and Outcomes | Timeline | Responsible Party
Objective 1.3: Using a strategic approach, continue to develop video sharing capabilities for NCR partners. | Continue to develop CCTV video sharing capability across NCRNet. | Oct 2013-Sept 2015 | RESF 1 w/SWICs
 | Develop mobile video sharing capability | Oct 2013-Sept 2015 | RESF 1 w/SWICs
 | Expand use of mobile video on DoT and other ESF-1 vehicles | Oct 2013-Sept 2015 | RESF 1
 | Develop Video Sharing ConOps, including any technical, legal & policy issues | Oct 2013-Sept 2015 | RESF 1 w/SWICs
 | Identify bandwidth constraints on video sharing and explore options for increasing as appropriate | Oct 2013-Sept 2015 | RESF 1 w/SWICs
 | Coordination & Collaboration with IT personnel over video sharing and mobile bandwidth | Oct 2013-Sept 2015 | RESF 1

## Slide 14: Snapshot from Work Plan: Goal 2
Objective | ESF 16 Tasks and Outcomes | Timeline | Responsible Party
Objective 2.1: NCR partners employ a variety of means to collect, analyze, and disseminate accurate and timely information to ensure appropriate officials have situational awareness. | Foster participation of EOC staff in WebEOC training and exercises | Sept 2013-Sept 2015 | RESF 16/RESF 5/Fairfax County OEM
 | Ensure each Volunteer Coordinator has access to appropriate regional boards in WebEOC | Sept 2013-Sept 2015 | RESF 16/RESF 5/Fairfax County OEM
 | Ensure Volunteer Coordinators receive training in RICCS usage so they can send messages to ESF 16 groups | Sept 2013-Sept 2015 | RESF 16/COG
 | Along with CIOs, analyze/undertake creation of a regional virtual system for Donations and Volunteer Management to foster information sharing | Sept 2013-Sept 2015 | RESF 16/CIOs

## Slide 15: Snapshot from Work Plan: Goal 3
Objective | CIP Tasks and Outcomes | Timeline | Responsible Party
Objective 3.2: Undertake Regional planning for loss of public and private sector critical infrastructure. | Build on NCR THIRA to prioritize CIP investments in the NCR | Oct 2013-Sept 2015 | CIP/EOCs/Private Sector Partners
 | Share best practices in CIP to develop regional programs | Oct 2013-Sept 2015 | CIP RPWG
 | Coordinate with other RESFs, especially RESF 5, on CIP priorities and projects | Oct 2013-Sept 2015 | CIP RPWG/ESFs
 | Work with Emergency Managers and Emergency Planners to develop program to prioritize and undertake planning efforts within priority sectors | Oct 2013-Sept 2015 | CIP RPWG/ RESF 5/ Planners
 | Conduct Cybersecurity Exercise | Fall 2014 | ETOP/CIP/Subgrantee
 | Develop water outage regional plan in coordination with Emergency Managers | Oct 2013-Sept 2015 | CIP RPWG/ RESF 5/ Planners
 | Participate in FY12 UASI cybersecurity regional planning project | Oct 2013-May 2014 | CIP RPWG/ Arlington County
 | Implement NCR Critical Infrastructure Database FY12 UASI project | Oct 2013-May 2014 | CIP RPWG/VAHS

## Slide 16: Snapshot from Work Plan: Goal 4
Objective | ESF 5 Tasks and Outcomes | Timeline | Responsible Party
Objective 4.6: Identify and work to resolve policy, procedural, and legal issues that have an impact on NCR regional homeland security and emergency management activities. | Revise RECP | Sept 2013-Sept 2015 | ESF 5/Planners
 | Revise 1st Hour Checklist | Sept 2013-Sept 2015 | ESF 5/Planners
 | Develop Mutual Aid Operations Plan | Sept 2013-Sept 2015 | ESF 5/Planners
 | In coordination with COG Attorney Committee, and other relevant parties, to resolve IMT deployment issues. Develop local sustainment model for IMT, including succession model | Sept 2013-Sept 2015 | ESF 5
 | Participate in annual Fire/Police/Emergency Management meeting | Sept 2013-Sept 2015 | ESF 5/ ESF4/ ESF 13
 | Identify and work to resolve regional policy, procedural, and legal issues | Sept 2013-Sept 2015 | ESF 5

## Slide 17: Next Steps
EPC approval of Updated Plan
Deliver NCR Strategic Plan to new PMO
PMO will continue to work with RESF/RPWGs to capture and update their tasks in support of the Plan
  Work Plans referenced at monthly meetings
  Annual update of Work Plans
PMO will lead effort to write new NCR Homeland Security Plan in 2015

## Slide 18: Contact Information
Sue Snider
  571-238-7913
  sue.snider@vdem.virginia.gov
Stuart Freudberg
  202-962-3340
  sfreudberg@mwcog.org
Markus Rauschecker
  301-738-6245
  mrauschecker@law.umaryland.edu