## Summary
FY 2011 TPB TIGER Grant Application - Cost and Schedule
[5 empty] | FY2012 |  | FY 2013 |  |  |  | FY 2014 |  |  |  | FY 2015 |  |  |  | FY 2016 |  |  |  | TOTALS
[5 empty] | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Total Budget | TIGER | Local | Match
District Of Columbia
Fort Totten / 1st Place-Galloway Road Access Improvement Project | 4171050 | 3336840 | 834210 | 20% | FY2012 3Q: 258750; FY2012 4Q: 258750; FY 2013 1Q: 0; FY 2013 2Q: 1216336.485; FY 2013 3Q: 1216336.485; FY 2013 4Q: 1220877.03 | 4171050
Maryland
Forest Glen Metrorail Access Project | 17600000 | 14080000 | 3520000 | 20% | 105000 | 105000 | 450000 | 450000 | 450000 | 950000 | 1115000 | 1115000 | 927500 | 1135833.3333 | 1240000 | 1240000 | 922083.3333 | 1692916.6667 | 1820000 | 2185625 | 1696041.6667 |  | 17600000
Pedestrian Safety Measures for the New Carrollton Metrorail Station | 953419.6 | 682735.68 | 270683.92 | 28.39% | FY2012 3Q: 50000; FY2012 4Q: 50000; FY 2013 1Q: 52267.5; FY 2013 2Q: 105052.5; FY 2013 3Q: 346725; FY 2013 4Q: 297624.6; FY 2014 1Q: 51750 | 953419.6
Twinbrook Metro Station: Pedestrian Safety Improvements | 501589.98 | 401271.984 | 100317.996 | 20% | FY 2014 1Q: 246810.1365; FY 2014 2Q: 254779.8435 | 501589.98
West Hyattsville Metrorail Station Access Improvements | 710250 | 542750 | 167500 | 23.58% | FY 2013 2Q: 37500; FY 2013 3Q: 257583.3333; FY 2013 4Q: 267583.3333; FY 2014 1Q: 147583.3333 | 710250
Virginia
Arlington Army Navy Drive Multimodal Access Improvement Project | 6838878.74 | 4965982.992 | 1872895.748 | 27.39% | FY 2013 1Q: 1011328.74; FY 2013 2Q: 135050; FY 2013 3Q: 1428300; FY 2013 4Q: 1428300; FY 2014 1Q: 1428300; FY 2014 2Q: 1407600 | 6838878.74
Bicycle Lockers at VRE Stations | 283600.35 | 226880.28 | 56720.07 | 20% | FY 2013 3Q: 65555; FY 2013 4Q: 108655; FY 2014 1Q: 56905; FY 2014 2Q: 44505; FY 2014 3Q: 7980 | 283600
TOTAL Project Implementation Cost | 31058788.67 | 24236460.936 | 6822327.734 | 21.97% | 413750 | 413750 | 1513596.24 | 1943938.985 | 3764499.8183 | 4273039.9633 | 3046348.4698 | 2821884.8435 | 935480 | 1135833.3333 | 1240000 | 1240000 | 922083.3333 | 1692916.6667 | 1820000 | 2185625 | 1696041.6667 |  | 31058788.32
Jobs Created/Retained |  |  |  |  | 4.4973 | 4.4973 | 16.4521 | 21.1298 | 40.9185 | 46.4461 | 33.1125 | 30.6727 | 10.1683 | 12.346 | 13.4783 | 13.4783 | 10.0226 | 18.4013 | 19.7826 | 23.7568 | 18.4352 |  | 337.5955
Direct, On-Project Jobs |  |  |  |  | 2.8783 | 2.8783 | 10.5294 | 13.5231 | 26.1878 | 29.7255 | 21.192 | 19.6305 | 6.5077 | 7.9014 | 8.6261 | 8.6261 | 6.4145 | 11.7768 | 12.6609 | 15.2043 | 11.7986 |  | 216.0611
Induced Jobs |  |  |  |  | 1.619 | 1.619 | 5.9228 | 7.6067 | 14.7307 | 16.7206 | 11.9205 | 11.0422 | 3.6606 | 4.4446 | 4.8522 | 4.8522 | 3.6082 | 6.6245 | 7.1217 | 8.5524 | 6.6367 |  | 121.5344

## DC Ftotten
FY 2011 TPB TIGER Grant Application - Cost and Schedule | [11 empty] | 2013
[6 empty] | FY 2012 |  |  |  | FY 2013
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
Fort Totten Station Access
Included in TIGER Request
1. Final Design & Engineering | Design | DDOT | Contractor | 500000 | TIGER
Complete final design (30% to 100%) and engineering for project. | [5 empty] | FY 2012 3Q: 250000; FY 2012 4Q: 250000
2. Construction | Construction | DDOT | Contractor | 3530000 | TIGER
2.1 1st Place NE Section
Excavaton, Milling, grading, curb and gutter, asphalt, pavement markings, catch basins, street lights | Procure | DDOT | Contractor | 752641 |  | FY 2013 2Q: 250880.3333; FY 2013 3Q: 250880.3333; FY 2013 4Q: 250880.3333
2.2 WMATA property Section
Excavaton, Milling, grading, curb and gutter, asphalt, pavement markings, catch basins, street lights, rain garden | Procure | DDOT | Contractor | 1711513 |  | FY 2013 2Q: 570504.3333; FY 2013 3Q: 570504.3333; FY 2013 4Q: 570504.3333
2.3 Pedestrian Plaza
Pavers, secure bike parking, landscape | Procure | DDOT | Contractor | 622380 |  | FY 2013 2Q: 207460; FY 2013 3Q: 207460; FY 2013 4Q: 207460
2.4 Galloway Street NE Section
Excavaton, Milling, grading, curb and gutter, asphalt, pavement markings, retaining wall | Procure | DDOT | Contractor | 439079 |  | FY 2013 2Q: 146359.6667; FY 2013 3Q: 146359.6667; FY 2013 4Q: 146359.6667
Total Construction Costs (not rounded) |  |  |  | 3525613 |  | FY 2013 4Q: 4387
Project Implementation Cost |  |  |  | 4030000 |  |  |  | 250000 | 250000 | 0 | 1175204.3333 | 1175204.3333 | 1179591.3333
COG PM Costs (3.5%) |  |  |  | 141050 |  |  |  | 8750 | 8750 | 0 | 41132.1517 | 41132.1517 | 41285.6967
TOTAL Project Implementation Cost |  |  |  | 4171050 |  |  |  | 258750 | 258750 | 0 | 1216336.485 | 1216336.485 | 1220877.03 | 4171050
Total TIGER Funds |  |  |  | 3336840 | 80%
Total Other Funds (% match) |  |  |  | 834210 | 20%
0
0

## MC F Glen
Forest Glen Pedestrian Passageway | [23 empty] | CY 2016
FY 2011 TPB TIGER Grant Application - Cost and Schedule | [5 empty] | FY 2012 |  |  |  | FY 2013 |  |  |  | FY 2014 |  |  |  | FY 2015 |  |  |  | FY 2016
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
Forest Glen Pedestrian Passageway under
Georgia Avenue
1. Planning | Design | County | County | 210000 | TIGER
Management and Review (Mont. County) |  |  |  | 50000 |  | FY 2012 3Q: 25000; FY 2012 4Q: 25000 | 50000
Agency (SHA and WMATA) Review |  |  |  | 10000 |  | FY 2012 3Q: 5000; FY 2012 4Q: 5000 | 10000
Planning/NEPA Documentation |  |  |  | 150000 |  | FY 2012 3Q: 75000; FY 2012 4Q: 75000 | 150000
2. Final Design and Engineering | Design | County | County | 3090000
Management and Review (Mont. County) |  |  |  | 150000 |  | FY 2013 1Q: 37500; FY 2013 2Q: 37500; FY 2013 3Q: 37500; FY 2013 4Q: 37500 | 150000
Management and Administration (MWCOG) |  |  |  | 600000 | [5 empty] | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 |  | 600000
Agency (SHA and WMATA) Review |  |  |  | 100000 |  | FY 2013 1Q: 25000; FY 2013 2Q: 25000; FY 2013 3Q: 25000; FY 2013 4Q: 25000 | 100000
Final design and engineering for project |  |  |  | 1390000 |  | FY 2013 1Q: 347500; FY 2013 2Q: 347500; FY 2013 3Q: 347500; FY 2013 4Q: 347500 | 1390000
Construction Management and Inspection (Mont. County) |  |  |  | 850000 |  | FY 2014 1Q: 75000; FY 2014 2Q: 75000; FY 2014 3Q: 75000; FY 2014 4Q: 75000; FY 2015 1Q: 75000; FY 2015 2Q: 75000; FY 2015 3Q: 80000; FY 2015 4Q: 80000; FY 2016 1Q: 80000; FY 2016 2Q: 80000; FY 2016 3Q: 80000 | 850000
3. Land Acquisition | Acquisition | County | County | 500000
Acquire required Right-of-Way, Easements |  |  |  | 500000 |  | FY 2013 4Q: 500000 | 500000
4. Construct Pedestrian Passageway | Construction | County | Contractor | 13300000
Utility Relocation |  |  |  | 2000000 |  | FY 2014 1Q: 1000000; FY 2014 2Q: 1000000 | 2000000
Install Support of Excavation |  |  |  | 3250000 |  | FY 2014 3Q: 812500; FY 2014 4Q: 812500; FY 2015 1Q: 812500; FY 2015 2Q: 812500 | 3250000
Excavate and Install Temporary Bridge |  |  |  | 1250000 |  | FY 2014 4Q: 208333.3333; FY 2015 1Q: 312500; FY 2015 2Q: 312500; FY 2015 3Q: 312500; FY 2015 4Q: 104166.6667 | 1250000
Construct Ped. Passageway and Station Tie-In |  |  |  | 5875000 |  | FY 2015 3Q: 489583.3333; FY 2015 4Q: 1468750; FY 2016 1Q: 1468750; FY 2016 2Q: 1468750; FY 2016 3Q: 979166.6667 | 5875000
Conduct Roadway Restoration |  |  |  | 925000 |  | FY 2016 1Q: 231250; FY 2016 2Q: 346875; FY 2016 3Q: 346875 | 925000
5. Bike Share Stations | Construction | County |  | 500000
Construct Bike Share Stations |  |  |  | 500000 |  | FY 2016 2Q: 250000; FY 2016 3Q: 250000 | 500000
TOTAL Project Implementation Cost |  |  |  | 17600000 |  | 0 | 0 | 105000 | 105000 | 450000 | 450000 | 450000 | 950000 | 1115000 | 1115000 | 927500 | 1135833.3333 | 1240000 | 1240000 | 922083.3333 | 1692916.6667 | 1820000 | 2185625 | 1696041.6667 |  | 17600000
Total TIGER Funds |  |  |  | 14080000
Total Other Funds (% match) |  |  |  | 3520000 | 20%

## PG NewC
FY 2011 TPB TIGER Grant Application - Cost and Schedule | [7 empty] | 2013
[6 empty] | FY 2013 |  |  |  | FY 2014
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
New Carrollton Safety Measures for the New Carrollton Metro Station
NOT FUNDED BY TIGER - Included in Local Matching
1. Final Design & Engineering | Design | County | County | 100000 | County
Complete Final Design | [5 empty] | FY 2013 1Q: 50000; FY 2013 2Q: 50000
2. Construct Pedestrian Crossings |  |  |  | 824560 | TIGER
2.1 Sign Installation on Garden City Drive near Metro Staton Entrance |  |  |  | 500 | 400 | FY 2013 3Q: 500 | 500
2.2 Bike facility improvements for 85th Avenue from Annapolis Road to Harkins Road |  |  |  | 6500 | 5200 | FY 2013 4Q: 6500 | 6500
2.3 Extend the West median for better pedestrian refuge on Harkins Road at West Lanham Drive |  |  |  | 30000 | 24000 | FY 2014 1Q: 15000; FY 2014 2Q: 15000 | 30000
2.4 Install six new lights along roadway for Ellin Road |  |  |  | 90000 | 72000 | FY 2014 1Q: 45000; FY 2014 2Q: 45000 | 90000
2.5 Upgrade existing geometry and signal to the latest ADA standards for pedestrian and overall safety
at Garden City Drive at Corporate Place |  |  |  | 270000 | 216000 | FY 2013 3Q: 50000; FY 2013 4Q: 50000; FY 2014 1Q: 100000; FY 2014 2Q: 70000 | 270000
2.6 Install pedestrian walkway on Ellin Road From Veterans Parkway to Emerson Place |  |  |  | 200760 | 160608 | FY 2013 4Q: 25000; FY 2014 1Q: 50000; FY 2014 2Q: 75760; FY 2014 3Q: 50000 | 200760
2.7 Install pedestrian walkway on east side Garden City Drive |  |  |  | 151800 | 121440 | FY 2013 4Q: 20000; FY 2014 1Q: 50000; FY 2014 2Q: 81800 | 151800
2.8 Provide trash receptacles (WMATA) | Quantity 10 |  |  | 15000 | 12000 | FY 2014 1Q: 15000 | 15000
2.9 Provide 10 benches (WMATA |  |  |  | 15000 | 12000 | FY 2014 1Q: 15000 | 15000
3.0 Consolidate Bus Stops on Annapolis Road (WMATA) |  |  |  | 15000 | 12000 | FY 2014 1Q: 15000 | 15000
3.1 Move bus Stop closer to intersection of Annapolis Road and 85th Ave |  |  |  | 15000 | 12000 | FY 2014 1Q: 15000 | 15000
3.2 Move Bus Stop close to Intersection of Annapolis Road and Riverdale Road |  |  |  | 15000 | 12000 | FY 2014 1Q: 15000 | 15000
Project Implementation Cost |  |  |  | 924560
Project Construction Costs |  |  |  | 824560 | 659648 |  |  | 50500 | 101500 | 335000 | 287560 | 50000 |  | 824560
COG PM Costs |  |  |  | 28859.6 |  |  |  | 1767.5 | 3552.5 | 11725 | 10064.6 | 1750 |  | 28859.6
Total Construction Costs (inc COG PM) |  |  |  | 853419.6 | 682735.68 | 0 | 0 | 52267.5 | 105052.5 | 346725 | 297624.6 | 51750 |  | 853419.6
TOTAL Project Implementation Cost |  |  |  | 953419.6 |  | 50000 | 50000 | 52267.5 | 105052.5 | 346725 | 297624.6 | 51750 |  | 953419.6
Total TIGER request |  |  |  | 682735.68
Total Other Funds |  |  |  | 270683.92 | 28.39%
[6 empty] | FY 2014 4Q: 0 |  | 0 | 0 | 0
[15 empty] | 0 |  | 0

## RV Tbrook
FY 2011 TPB TIGER Grant Application - Cost and Schedule
[7 empty] | FY 2013 |  |  |  | FY 2014
[7 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project (By Study Corridor) | Activity | Lead Agency | Workforce | Budget | Existing/ New Infrastructure | Funding Source
Twinbrook Station Pedestrian Improvements
1. Construction - Improvements on/near Halpine Road | [5 empty] | TIGER
Halpine / E. Jefferson
Raised Intersection | Construction | Rockville | Contractor | 37260 | New |  | FY 2014 1Q: 18630; FY 2014 2Q: 18630
High Visibility Crosswalk | Installation | Rockville | Contractor | 6210 | Modify Existing |  | FY 2014 2Q: 6210
Advanced Stop Bar Realignment | Installation | Rockville | Contractor | 745.2 | Modify Existing |  | FY 2014 2Q: 745.2
Halpine / Congressional Shopping Center Driveway
High Visibility Crosswalk | Installation | Rockville | Contractor | 9563.4 | Modify Existing |  | FY 2014 2Q: 9563.4
Halpine / Rockville Pike
High Visibility Crosswalk | Installation | SHA | Contractor | 16394.4 | Modify Existing |  | FY 2014 1Q: 16394.4
Halpine / Chapman
Curb Extensions | Construction | Rockville | Contractor | 49680 | New |  | FY 2014 1Q: 24840; FY 2014 2Q: 24840
High Visibility Crosswalk | Installation | Rockville | Contractor | 5464.8 | New |  | FY 2014 2Q: 5464.8
2. Construction - Improvements on/near Lewis Avenue | [5 empty] | TIGER
Lewis / Rockland
High Visibility Crosswalk | Installation | Rockville | Contractor | 5464.8 | New |  | FY 2014 1Q: 5464.8
Advanced Stop Bar Realignment | Installation | Rockville | Contractor | 621 | New |  | FY 2014 1Q: 621
Lewis / Halpine
High Visibility Crosswalk | Installation | Rockville | Contractor | 4098.6 | New |  | FY 2014 1Q: 4098.6
Construct Sidewalk on south side of Halpine | Construction | Rockville | Contractor | 9936 | New |  | FY 2014 1Q: 9936
Wayfinding Signs to Metrorail | Installation | Rockville | Contractor | 1242 | New |  | FY 2014 1Q: 1242
4. Construction - Improvements near Rockville Pike and Chapman Avenue | [5 empty] | TIGER
Chapman - mid block
Construct Curb Extensions | Construction | Rockville | Contractor | 6210 | New |  | FY 2014 1Q: 6210
Chapman / Bouic
Curb Extensions | Construction | Rockville | Contractor | 39744 | New |  | FY 2014 1Q: 19872; FY 2014 2Q: 19872
Chapman / Thompson
Curb Extensions | Construction | Rockville | Contractor | 80730 | New |  | FY 2014 1Q: 40365; FY 2014 2Q: 40365
Chapman / Twinbrook
Elimination of EB Twinbrook " Hot Right" | Construction | Rockville | Contractor | 93150 | Modify Existing |  | FY 2014 1Q: 46575; FY 2014 2Q: 46575
High Visibility Crosswalk | Installation | Rockville | Contractor | 13041 | New |  | FY 2014 2Q: 13041
Advanced Stop Bar Realignment | Installation | Rockville | Contractor | 2235.6 | Modify Existing |  | FY 2014 2Q: 2235.6
Addition of New Pedestrian Crossing Signals on East side | Construction | Rockville | Contractor | 37260 | New |  | FY 2014 1Q: 18630; FY 2014 2Q: 18630
Rockville Pike / Bouic
Construct Curb Extensions on Bouic | Construction | Rockville | Contractor | 12420 | New |  | FY 2014 1Q: 6210; FY 2014 2Q: 6210
Rockville Pike / Thompson
Construct Curb Extensions on Thompson | Construction | Rockville | Contractor | 8694 | New |  | FY 2014 1Q: 4347; FY 2014 2Q: 4347
Rockville Pike / Twinbrook
High Visibility Crosswalk | Installation | SHA | Contractor | 15028.2 | Modify Existing |  | FY 2014 1Q: 7514.1; FY 2014 2Q: 7514.1
Rockville Pike / Bou
High Visibility Crosswalk | Installation | SHA | Contractor | 15028 | Modify Existing |  | FY 2014 1Q: 7514; FY 2014 2Q: 7514
5. Construction - Improvements on Rockville Pike, north of Twinbrook Station | [5 empty] | TIGER
Rockville Pike / Congressional Lane
High Visibility Crosswalk | Installation | SHA | Contractor | 14407 | Modify Existing |  | FY 2014 2Q: 14407
TOTAL Project Implementation Cost |  |  |  | 484628 |  |  | FY 2014 1Q: 238463.9; FY 2014 2Q: 246164.1
COG PM Costs (3.5%) |  |  |  | 16961.98 |  |  | FY 2014 1Q: 8346.2365; FY 2014 2Q: 8615.7435
TOTAL Project Implementation Cost |  |  |  | 501589.98 |  |  | FY 2014 1Q: 246810.1365; FY 2014 2Q: 254779.8435
TIGER |  |  |  | 401271.984
Local (% match) |  |  |  | 100317.996 | 20%

## PG WH
FY 2011 TPB TIGER Grant Application - Cost and Schedule - West Hyattsville ONLY Project
[6 empty] | FY 2013 |  |  |  | FY 2014
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
Ager Road Green Road Project - Project Start Date - January 2012
West Hyattsville Access Improvments - Project Start Date - January 2012
NOT FUNDED BY TIGER - Included in Local Matching
1. Planning, Design & Engineering | Design | County | Consultant |  | County
Construction - Start Date - September 2013 | Construction | County | Contractor |  | TIGER 80%
West Hyattsville Project Access Improvements
| Jamestown Road Sidewalk Design |  |  | 37500 |  | FY 2013 2Q: 37500
(note: Design costs are not a part of Tiger request)
| Jamestown Road Sidewalk Construction |  |  | 250000 | 200000 | FY 2013 3Q: 50000; FY 2013 4Q: 100000; FY 2014 1Q: 100000
| WMATA Secure Bike Station |  |  | 400000 | 320000 | FY 2013 3Q: 200000; FY 2013 4Q: 160000; FY 2014 1Q: 40000
Project Implementation Cost |  |  |  | 687500 |  | FY 2013 3Q: 250000; FY 2013 4Q: 260000; FY 2014 1Q: 140000
Construction Costs |  |  |  | 650000 | 520000
Plus COG PM Costs (3.5%) |  |  |  | 22750 | 22750 | FY 2013 3Q: 7583.3333; FY 2013 4Q: 7583.3333; FY 2014 1Q: 7583.3333
TOTAL Project Construction Costs |  |  |  | 672750 | 542750 | FY 2013 2Q: 37500; FY 2013 3Q: 257583.3333; FY 2013 4Q: 267583.3333; FY 2014 1Q: 147583.3333
TOTAL Project Implementation Cost |  |  |  | 710250 |  | FY 2014 1Q: 710250
Total TIGER Funds |  |  |  | 542750 |  | FY 2014 2Q: 672750
Total Other Funds (% match) |  |  |  | 167500 | 23.58%

## Arl A-N
FY 2011 TPB TIGER Grant Application - Cost and Schedule
[6 empty] | FY 2013 |  |  |  | FY 2014 |  |  |  | FY 2015 |  |  |  | FY 2016 |  |  |  | FY 2017
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
Combined Pentagon / Pentagon City / Crystal City Access Improvement Project
1. Planning | NOT FUNDED BY TIGER - Included in Local Matching
Army Navy Drive | Planning
30% design |  | FHWA | 270000 |  | FHWA | FY 2013 1Q: Finished as of FY 2011.
100% design and site coordination |  | Arlington |  | 620000 | Arlington | FY 2013 1Q: 104000; FY 2013 2Q: 104000; FY 2013 3Q: Completed mid-FY2013
Bikesharing 5 initial stations | Planning
Plan station locations |  | Arlington |  | 2500 | Arlington | FY 2013 1Q: To be completed FY2012
Obtain environmental clearance |  | Arlington |  | 3200 | Arlington | FY 2013 1Q: To be completed FY2012
Bikesharing 5 additional stations | Planning
Plan station locations |  | Arlington |  | 2500 | Arlington | FY 2013 1Q: To be completed FY2012
Obtain environmental clearance |  | Arlington |  | 3200 | Arlington | FY 2013 1Q: To be completed FY2012
Total Planning Costs - all Local |  |  |  | 631400
2. Implementation |  |  |  | Overall | TIGER
Army Navy Drive Construction | Construction
Arlington portion |  |  |  | 1110000 | Arlington | FY 2013 3Q: 1100000; FY 2013 4Q: 1100000; FY 2014 1Q: 1100000; FY 2014 2Q: 1090000
TIGER portion |  |  |  | 4390000 | TIGER | FY 2013 3Q: 280000; FY 2013 4Q: 280000; FY 2014 1Q: 280000; FY 2014 2Q: 270000
Bikesharing 5 initial stations | Construction
Procurement |  |  |  | 233782 | TIGER | FY 2013 1Q: 233782
Installation |  |  |  | 15000 | TIGER | FY 2013 2Q: 15000
Bikesharing 5 additional stations | Construction
Procurement |  |  |  | 233782 | TIGER | FY 2013 1Q: 233782
Installation |  |  |  | 15000 | TIGER | FY 2013 2Q: 15000
Total Construction Costs |  |  |  | 5997564 | 4798051.2
COG PM (3.5%) of construction |  |  |  | 209914.74 |  | FY 2013 1Q: 16364.74; FY 2013 2Q: 1050; FY 2013 3Q: 48300; FY 2013 4Q: 48300; FY 2014 1Q: 48300; FY 2014 2Q: 47600
TOTAL |  |  |  | 6207478.74 | 4965982.992
TOTAL Project Implementation Cost |  |  |  | 6838878.74
[6 empty] | 1011328.74 | 135050 | 1428300 | 1428300 | 1428300 | 1407600 |  | 6838878.74
Total TIGER Funds (%) |  |  |  | 4965982.992 | 72.61%
Total Other Funds (% match) |  |  |  | 1872895.748 | 27.39%

## VRE
FY 2011 TPB TIGER Grant Application - Cost and Schedule
CY 2013
[6 empty] | FY 2013 |  |  |  | FY 2014
[6 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Project | Activity | Lead Agency | Workforce | Budget | Funding Source
VRE Bike Lockers
1. Install Bike Lockers |  |  |  | 283600.35 | TIGER
Install bike lockers at eight (8) locations
Broad Run
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration |  | VRE | VRE | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Rippon
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE | 5882.45 |  | FY 2013 3Q: 1470; FY 2013 4Q: 1470; FY 2014 1Q: 1470; FY 2014 2Q: 1473
Woodbridge
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Manassas
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Manassas Park
Purchase lockers | Procure | VRE | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE | VRE | 5199.35 |  | FY 2013 3Q: 1300; FY 2013 4Q: 1300; FY 2014 1Q: 1300; FY 2014 2Q: 1299
Rolling Rd.
Purchase lockers | Procure | VRE/Fairfax Co. | Manufacturer | 14500 |  | FY 2013 3Q: 7250; FY 2013 4Q: 7250
Prepare site | Construct | VRE/Fairfax Co. | Contractor | 7500 |  | FY 2013 4Q: 3750; FY 2014 1Q: 3750
Install | Construct | VRE/Fairfax Co. | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE/Fairfax Co. | VRE/Fairfax Co. | 4462.5 |  | FY 2013 3Q: 1115; FY 2013 4Q: 1115; FY 2014 1Q: 1115; FY 2014 2Q: 1118
Lorton
Purchase lockers | Procure | VRE/Fairfax Co. | Manufacturer | 11600 |  | FY 2013 3Q: 5800; FY 2013 4Q: 5800
Prepare site | Construct | VRE/Fairfax Co. | Contractor | 8200 |  | FY 2013 4Q: 4100; FY 2014 1Q: 4100
Install | Construct | VRE/Fairfax Co. | Contractor | 2000 |  | FY 2014 2Q: 2000
Permits, Inspection, Administration | Construct | VRE/Fairfax Co. | VRE/Fairfax Co. | 4157.8 |  | FY 2013 3Q: 1040; FY 2013 4Q: 1040; FY 2014 1Q: 1040; FY 2014 2Q: 1038
Franconia-Springfield
Purchase lockers + bike racks | Procure | VRE/Fairfax Co. | Manufacturer | 19400 |  | FY 2013 3Q: 9700; FY 2013 4Q: 9700
Prepare site | Construct | VRE/Fairfax Co. | Contractor | 49700 |  | FY 2013 4Q: 16500; FY 2014 1Q: 16500; FY 2014 2Q: 16700
Install | Construct | VRE/Fairfax Co. | Contractor | 3000 |  | FY 2014 3Q: 3000
Permits, Inspection, Administration | Construct | VRE/Fairfax Co. | VRE/Fairfax Co. | 24900.2 |  |  |  | 4980 | 4980 | 4980 | 4980 | 4980
TOTAL Project Implementation Cost |  |  |  | 283600.35 |  |  |  | 65555 | 108655 | 56905 | 44505 | 7980
Total TIGER Funds |  |  |  | 226880.28
Total Other Funds (% match) |  |  |  | 56720.07