## Slide 1
NCR Urban Areas Security Initiative Grants Update
09 November 2011
SAA Brief to the NCR Emergency Preparedness Council

## Slide 2
FY11 Awards Update
FY08 UASI Grant Close-Out
FY09 UASI Grant Update
FY10 UASI Grant Update
FY12 UASI Forecast
Agenda
Notes: 2

## Slide 3
FY 2011 award is $59,392,477
SAA has issued 113 sub-grant awards to NCR jurisdictions (7 pending).
Subgrantees have been given 9/1/2011 – 10/31/2013 to complete their projects.
Next Steps:
  Subgrantee acceptance of awards (Council approvals)
  Environmental / Historic Preservation Reviews (as needed)
  Procurement
FY11 UASI
Awards
FY 2011 UASI period of performance is:
September 1, 2011 – August 31, 2014
Notes: 3

## Slide 4
FY08 UASI award - $59.8 Million
All sub-grants have expired. Deadline for sub-grantees to submit final invoices for reimbursement to the SAA was October 10, 2011.
Final liquidation will conclude by November 29, 2011.
The 2008 UASI grant will be closed out at 100% fully expended.
The FY08 UASI period of performance expired on 31 August 2011
FY08 UASI
Close-Out
Notes: 4

## Slide 5
FY09 UASI award - $58,006,500
Currently, the FY09 UASI grant is 48% expended with 37% fully reimbursed to subgrantees
Sub-grants that were not issued extensions expired at the end of September 2011. Extensions were issued on a case by case basis as far out as April 30, 2012.
09 reimbursements have picked up noticeably in the last few months
FY09 UASI
Overview
FY 09 UASI period of performance is August 01, 2009 – July 31, 2012
Notes: 5
Still need about $18M of project expenditures to be built in NCRGMS spend plans.

## Slide 6: FY2009 UASI Spending Status
Chart: 
| Complete | Invoiced | On Order | Allocated to Projects
 | 21845608 | 6054119 | 6153381 | 23953392

## Slide 7
FY10 UASI award - $59,392,477
Currently, the FY10 UASI grant is 15% expended with 8% fully reimbursed to subgrantees.
Original sub-grant period of performance was 8/01/2010 – 10/30/2012
Extensions will be considered for projects in Spring 2012.
FY10 UASI
Overview
FY 10 UASI period of performance is
August 01, 2010 – July 31, 2013
Notes: 7

## Slide 8: FY2010 UASI Spending Status
Chart: 
| Complete | Invoiced | On Order | Allocated to Projects
 | 4651288 | 4274499 | 4573842 | 45892848

## Slide 9
Congress has not passed a FY2012 budget for DHS. Grant Guidance may not be issued until Jan-Feb 2012.
The NCR should begin its prioritization of needs early in order to be ready when the Grant Guidance is released
SAA is working with the SPG/CAO and R-ESF Chairs to lay out the timeline and process
FY12 UASI
Forecast
Appropriations | FEMA Preparedness Grants (all) | UASI
2010 Appropriation | $3,088,000,000 | $887,000,000
2011 Appropriation | $2,276,438,000 | $704,588,000
2012 House Proposed Bill | $1,157,337,000 | (no specific allocation)
2012 Senate Proposed Bill | $1,595,000,000 | $400,000,000
Notes: 9

## Slide 10
Tim Fitzsimmons
Grants Division Chief
D.C. HSEMA
202-727-6155
Timothy.Fitzsimmons@dc.gov
Notes: 10