## Slide 1
NCR Urban Areas Security Initiative Grants Update
14 September 2011
SAA Brief to the NCR Emergency Preparedness Council

## Slide 2
FY11 Award Status and Project Plans
FY08 UASI Grant Update
FY09 UASI Grant Update
FY10 UASI Grant Update
Agenda
Notes: 2

## Slide 3
FY 2011 award is $59,392,477
SAA has sent out requests to all prospective subgrantees notifying them of the project award and amount, and has requested all PMP’s be completed and submitted by Sept. 02, 2011.
SAA will review all project PMP’s and will issue awards to subgrantees with an approved PMP by October 20, 2011
FY11 UASI
Overview
FY 2011 UASI period of performance is:
September 1, 2011 – August 31, 2014
Notes: 3

## Slide 4
FY08 UASI award - $59.8 Million
All sub-grants have expired. The only remaining activity is collecting final invoices and submitting to SAA for reimbursement. SAA has 90 days for liquidation.
Currently, 94% has been submitted to SAA, with 73% fully reimbursed to subgrantees.
The SAA anticipates closing out the grant at 100% fully expended and reimbursed to subrecipients.
The FY08 UASI period of performance expired on 31 August 2011
FY08 UASI
Overview
Notes: 4

## Slide 5: FY2008 UASI Spending Status
Chart: 
| Complete | Invoiced | On Order | Allocated to Projects
 | 43421038 | 12870062 | 539345 | 2970055
 | 0.7261 | 0.21522 | 0.0090191 | 0.049666

## Slide 6
FY09 UASI award - $58,006,500
Currently, the FY09 UASI grant is 37% expended with 30% fully reimbursed to subgrantees
Sub-grants that were not issued extensions will expire at the end of September 2011.
SAA anticipates an increase in the volume of FY09 reimbursements as the FY08 grant closes.
FY09 UASI
Overview
FY 09 UASI period of performance is August 01, 2009 – July 31, 2012
Notes: 6
Still need about $18M of project expenditures to be built in NCRGMS spend plans.

## Slide 7: FY2009 UASI Spending Status
Chart: 
| Complete | Invoiced | On Order | Allocated to Projects
 | 17342367 | 4422859 | 9763299 | 26477975

## Slide 8
FY10 UASI award - $59,392,477
Currently, the FY10 UASI grant is 8% expended with 5% fully reimbursed to subgrantees.
FY10 UASI
Overview
FY 10 UASI period of performance is
August 01, 2010 – July 31, 2013
Notes: 8

## Slide 9: FY2010 UASI Spending Status
Chart: 
| Complete | Invoiced | On Order | Allocated to Projects
 | 2839495 | 2037132 | 3707409 | 50808441

## Slide 10
Tim Fitzsimmons
Grants Division Chief
D.C. HSEMA
202-727-6155
Timothy.Fitzsimmons@dc.gov
Notes: 10